Subject: Power Train Ltd. – ADM4103A

To: Dr. Patrick Woodcock

From: Esther Melowsky, Patrick Tshitumbu Betu, Meghan Poirer, Jue Lu, Edwardette Salter

Group’s Email: mpoir060@uottawa.ca

Conclusion

Power Train’s Vice President, Claude Jones, must take five steps to undergo immediate action that will effectively manage their potential expansion. (1) Power Train (PT) will open an internal project office to manage resources and costs of projects. This office is required to complete the following four necessary steps. (2) Assign an HR employee to create engineer profiles to better differentiate the skill levels of each engineer. (3) Assign a PT employee to create criteria for selecting and scheduling projects based on priority to the company. (4) Hire software vendor, Lauren, to create heuristics that meet project requirements to then configure the multiproject software. (5) Schedule a training workshop for all PT project office employees to learn the new features of the multiproject software.

Analysis

Appendix A outlines the project office tasks to better understand the importance of an additional PT department. The project office will be responsible to keep on top of multiproject scheduling problems. This will create more jobs, and will lead to better response times in scheduling conflicts. This first step is essential in completing the other four steps. The second priority step would be, assigning an HR employee to create profiles for each engineer (Appendix B). These profiles will include educational information, salary, skills & expertise, and background information. By creating a database with different levels of engineers, the project office team will be able to estimate costs, check availability of resources, and assigning engineers to the correct tasks. This information will only be available to company employees, since it is highly sensitive material. Once the profiles are completed, PT will then assign an employee to create criteria for selecting and scheduling projects. Appendix C is a matrix that illustrates the decisions based on priority of project selection. The projects are ranked using a table of criteria based on scores of cost and urgency. Once the projects have been prioritized using the selection process, they then need to be scheduled for using resource leveling. On Appendix D, there are two types of project scheduling. The first graph illustrates an uneven and undesirable outcome. It is important that PT understands the important of scheduling tasks and outputting the most cost-effective resources to any specific project. The fourth priority step would be to hire the software vendor, Lauren, to create heuristics for the multiproject software. Heuristics will measure slack, duration, and task identification. The most optimal project will be chosen based on the least amount of slack of each task. As seen in Appendix E, we can see a sample resource-constrained project that selects a critical path of slack, which is equal to zero. These heuristics will be customized for PT, and will render efficient scheduling and minimal project delays. Lastly, once the multiproject software has been customized with both criteria and heuristics, PT will host a training workshop for its new project office staff. A memo will be sent out to all staff members to train them on the new features of the multiproject software (Appendix F). This step will be key in implementing these changes. Overall these five priority steps will enable PT to effectively manage a large number of projects effectively. By identifying scheduling problems and implementing new changes, PT’s strategy will allow for an increase in project contracts.