MGT5164 -Project Management

Assignment #1

Wedded Bliss

February 14, 2014

Table of Contents

General Information………………………………………………………………………...…3

Project Objective………………………………………………………………………………3

Project Scope………………………………………………………………………..…………3

#### Major Deliverables……………………………………………………………………………..4

#### Project Customers…………………………………………………………………………….4

#### Customer Requirements……………………………………………………………………..5

#### Customer needs and Key Attributes……………………………………………………….5

#### Project Stakeholders………………………………………………………………………….5

#### Project Manager and Authority Level…………………………………..………………….5

#### Project Milestones……………………………………………………………………………..5

Preliminary Budget……………………………………………………………………………6

#### Approval Requirements……………………………………………………………………....8

#### Bibliography…………………………………………………………………………………....8

Project Objective:

The object of this project is to join my daughter and her fiancée in legal matrimony as accepted by the Church and State while making it fun for all attending and involved. Other objectives include reaching (accommodating) the number of guests we aspired to within our budget, making money from the cash bar (projected to be $1500.00 profit from $3000.00 spent on refreshments) for the Bride and Groom and recording the event through pictures and video. The value we hope that this project adds to the organization (families involved) is to create a lasting memory for all involved and invited, and to provide everyone with a great time and to do it within the budget and time constraints without too much sacrifice or stress! This project will add joy, happiness and lasting memories and hopefully be the topic of conversation for years to come, as well as the legal ceremony to join the couple in Holy Matrimony. The project aligns with the strategic priorities of the organization (families) by keeping up with the traditions of Marriage and Religious ceremony and Church service that the families value very highly. The results we expect are to have a safe, great time with little hassle, on time and within budget. We view the deliverables as: A value terrific Wedding, meal, venue, entertainment and ceremony that is enjoyed by all within budget and schedule. The benefits to be realized are the joy experienced by all attending or involved and the legal coupling of the Bride And Groom. The problems to be resolved from this project are dealing with a limited budget and time constraints and making the relationship legal in the eyes of the Government and Church.

Project Scope:

The Project Scope is to plan a wedding for my daughter and her fiancée within a 3 month time frame and a budget of $20,000.00. To deliver a legal binding of the couple recognized by the Church and Government, a good time to all guests, a safe and fun celebration that is easy for all to navigate and participate in, with as little “surprises” as possible. Proposed Process and Statement of Work: To accomplish this task we will first have a Family meeting to discuss jobs and responsibilities with all those to be involved. We will discuss time and budget (allocation), the wants/needs of the celebrated couple and their families. We will agree on the venue for the reception, check availability and cost of the reception, Church and the Minister. We will allocate jobs to the appropriate parties, agree upon the Responsibility Assignment Matrix, draw up a schedule and a budget and get every ones approval and buy in. We will also discuss possible scope creep and how we can avoid it so we can stay on track and we’ll try very hard to consider any extra possibilities that may arise unexpectedly, by considering other scenarios from the experience of those in the group whom have been through or seen/heard of similar situations. As Project Manager I will keep a constant watch on the schedule, budget and Responsibility Assignment Matrix and make necessary adjustments and assure the project is meeting its goals.

#### Major Deliverables:

The Wedding ceremony, reception, meal, festivities/celebrations (entertainment), photos, video, gifts and the legal Marriage certificate.

#### Project Customers:

The families of the Bride and Groom and all guests.

#### Customer Requirements:

As we are the customers and the organization we are looking to achieve good value, great fun, little to no wasted time, with as few additional expenses, surprises and stresses as possible while staying within our time and budgetary requirements.

#### Customer needs and Key Attributes:

This project has been commissioned so that my Daughter can be married and have a celebration that she can remember forever. This will improve the customers situation (in this case my Daughter/the families) by providing lasting memories and hours of fun and celebration with the legal binding of her and her fiancée as recognized by Church and State.

#### Project Stakeholders:

The Bride and Groom and their families. All will play important roles in the project as outlined in the Statement of Work.

#### Project Manager and Authority Level:

I, the Father of the Bride, am acting as the Project Manager; I am authorized to allocate resources, manage and handle the funds, do the hiring, procurement and oversee the project as has been approved by the clients (both families and all friends involved).

#### Project Milestones

.

| Milestones | Deliverables | Date |
| --- | --- | --- |
| Meeting of all involved | Budget and schedule drawn up, Responsibility Assignment Matrix agreed upon, Decide on venue, Church and Minister. | First week |
| Purchase/rent attire | Wedding gown, Bridesmaid dresses, Groom & Groomsmen’s’ tuxes | Within 1st week!!! |
| Book Church and Minister | Church venue & Minister | Within first two weeks |
| Wedding licenses | Licenses | Within first two weeks |
| Book the venue hall | Hall | Within first three weeks |
| Gift Registry | Registry Identification process | Within 2 weeks (before invitations) |
| Design, print and send out invitations | Mailed invitations, resulting in responses to build actual guest list. | Within 2 weeks |
| Finalize Guest List | Hard copy of guest list | Within 5 weeks |
| Book caterer | Menu | Within 6 weeks |
| Book entertainment | Set List | Within 6 weeks |
| Purchase cake, flowers, decorations, food | Cake, flowers, flowers, decorations, food | Paid for within first month. |
| Purchase gifts/Wedding favours | Gifts/Wedding favours | Within 8 weeks |
| Wedding speeches | Speeches | The day before |
| Rehearsal dinner | Dinner, finalize plans | The night before |
| Hair and make-up | Good looking Bride | Wedding Day |
| Honeymoon | Joy & happiness/Grandchildren | After Wedding Day |

Preliminary Budget

| Notes | Break Down | Prices Break Down | Sub Totals | Notes |
| --- | --- | --- | --- | --- |
| Venue selection: wedding and reception |  |  | $ 500.00 |  |
|  | Hall | $ 250.00 |  |  |
|  | Church | $ 250.00 |  |  |
| Bridal shower |  |  | $ 1,000.00 |  |
| Photographer |  |  | $ 1,624.00 |  |
|  | Wedding Photographer | $ 1,200.00 |  |  |
|  | Wedding Videographer | $ 200.00 |  |  |
|  | Prints and/or Enlargements | $ 224.00 |  |  |
| Entertainment/Musicians |  |  | $ 750.00 |  |
| Cake design |  |  | $ 500.00 |  |
| Wedding attire |  |  | $ 1,350.00 |  |
|  | Wedding Dress | $ 1,000.00 |  |  |
|  | Dress Accessories | $ 100.00 |  |  |
|  | Headpiece and or Veil | $ 100.00 |  |  |
|  | Tuxedo / Suit / Other Accessories | $ 150.00 |  |  |
|  | Tuxedo / Suit / Other Rent/Purchase |  |  |  |
| Travel plans/Transportation for guests |  |  | $ 450.00 |  |
|  | Limo Rental | $ 100.00 |  | Family -Horses |
|  | Other Transportation | $ 350.00 |  |  |
| Accommodation for guests |  |  | $ 300.00 |  |
| Invitation design |  |  | $ 697.50 |  |
|  | Ceremony Programs | $ 100.00 |  | Home |
|  | Engagement Announcements | $ 100.00 |  | Home |
|  | Guest Book | $ 50.00 |  |  |
|  | Invitations & Reply Cards | $ 200.00 |  | Home |
|  | Postage | $ 127.50 |  |  |
|  | Reception Menus | $ 40.00 |  | Home |
|  | Save the Date Cards |  |  |  |
|  | Table Name and Escort/Place Cards | $ 40.00 |  | Home |
|  | Thank You Cards | $ 40.00 |  | Home |
| Flowers/Florist |  |  | $ 1,600.00 |  |
|  | Boutonnieres, Corsages | $ 125.00 |  |  |
|  | Bridal Bouquets | $ 125.00 |  |  |
|  | Bridesmaid Bouquet | $ 100.00 |  |  |
|  | Ceremony Decorations | $ 200.00 |  |  |
|  | Ceremony Flower Arrangements | $ 250.00 |  |  |
|  | Flower Girl Flowers | $ 50.00 |  |  |
|  | Flower Petals | $ 50.00 |  |  |
|  | Reception Decorations | $ 150.00 |  |  |
|  | Reception Flower Arrangements | $ 250.00 |  |  |
|  | Reception Table Centerpieces | $ 300.00 |  |  |
| Wedding Favours |  |  | $ 900.00 |  |
|  | Gifts for Attendants | $ 150.00 |  |  |
|  | Gifts for Parents | $ 150.00 |  |  |
|  | Tips (for all services) | $ 350.00 |  |  |
|  | Wedding Favors | $ 250.00 |  |  |
| Rehearsal dinner |  |  | $ 500.00 |  |
| Hair and makeup |  |  | $ 130.00 |  |
| Marriage commissioner |  |  | $ 320.00 |  |
| Marriage license |  |  | $ 70.00 |  |
| Caterers/ Reception dinner |  |  | $ 5,250.00 |  |
| Venue staff |  |  | $ 720.00 |  |
|  | Bar tender($140.00) & stock |  | $ 3,140.00 | Cash bar |
| Honeymoon |  | $ 3,500.00 |  | Paid for by In-Laws by their request. |
| Total |  |  | $ 19,801.50 |  |

#### Approval Requirements:

This Project charter and my role as Project Manager have been approved by the clients (both families and all friends involved).

Bibliography

http://www.statisticbrain.com/average-costs-of-an-american-wedding/, Statistics Brain

A Guide to the Project Management Body Of Knowledge, PMBOK guide, 5th Edition, PMI Inc. 2013.

http://webstyleguide.com/wsg3/1-process/8-project-charter.html, Web Style Guide, 3rd Edition, The Web Style Guide by Patrick J. Lynch and Sarah Horton

http://knolt.com/mairin/, Project Management in the Wedding Planning Business

Just another Knolt weblog

http://www.ad-esse.com/resources/documents/Articles/objectives_deliverables.pdf, Objectives vs. Deliverables

http://www.inc.com/tools/project-charter-example.html, inc. THE PLAYBOOK

http://abrachan.wordpress.com/, lifeatwork, by Abrachan Pudussery