## Answers 12 a & b
Systems Development Labor Hours
Date | Project Phase | Meeting Type | Start Time | End Time | Meeting Length | Users | SAs | Prgms | PQAs | Lvl-2 User Mgr | Lvl-2 User Mgr | Lvl-2 IS Mgr | Lvl-2 IS Mgr | Total Labor | Total Labor Hrs
2012-03-05 | SD | W | 20:35 | 22:05 | 1:30 | 2 | 2 |  |  | 2 |  |  |  | 6 | 0.375
2012-03-07 | SD | R | 14:00 | 15:25 | 1:25 | 3 | 2 |  |  | 2 | 1 | 1 |  | 9 | 0.53125
2012-03-24 | RA | W | 9:00 | 22:30 | 13:30 | 3 | 2 |  | 2 |  |  |  |  | 7 | 1900-01-02 22:30
2012-03-27 | RA | W | 8:00 | 20:25 | 12:25 | 2 | 2 | [6 empty] | 4 | 1900-01-01 01:40
2012-03-28 | RA | W | 8:30 | 20:00 | 11:30 | 2 | 1 |  | 2 |  |  |  |  | 5 | 1900-01-01 09:30
2012-03-25 | RA | R | 9:00 | 20:30 | 11:30 | 3 | 2 |  | 2 | 2 | 1 | 1 | 1 | 12 | 1900-01-04 18:00
2012-03-28 | CD | W | 8:00 | 20:00 | 12:00 | 2 | 2 | [6 empty] | 4 | 1900-01-01
2012-03-30 | CD | W | 14:00 | 15:30 | 1:30 | 2 | 2 |  | 2 |  |  |  |  | 6 | 0.375
2012-04-03 | CD | R | 16:00 | 17:00 | 1:00 | 2 | 2 |  | 2 | 2 |  | 1 | 1 | 10 | 0.41667
2012-04-05 | CD | W | 14:30 | 15:25 | 0:55 | 2 | 2 |  | 2 |  |  |  |  | 6 | 0.22917
2012-04-07 | CD | W | 9:25 | 20:45 | 11:20 | 3 | 3 |  | 2 |  |  |  |  | 8 | 1900-01-02 18:40
2012-04-09 | CD | W | 14:00 | 14:25 | 0:25 | 3 | 2 | 2 | 2 |  |  |  |  | 9 | 0.15625
2012-04-20 | CD | R | 15:30 | 17:00 | 1:30 | 3 | 1 |  | 2 | 2 | 1 | 1 | 1 | 11 | 0.6875
2012-04-22 | IM | W | 9:00 | 22:25 | 13:25 |  | 2 | 3 | 2 |  |  |  |  | 7 | 1900-01-02 21:55
2012-04-25 | IM | W | 22:00 | 22:25 | 0:25 | 2 | 2 | 3 | 2 |  |  |  |  | 9 | 0.15625
2012-04-26 | IM | W | 16:30 | 18:00 | 1:30 |  | 2 | 4 | 2 |  |  |  |  | 8 | 0.5
2012-04-22 | IM | W | 14:00 | 16:30 | 2:30 |  | 2 | 3 | 2 |  |  |  |  | 7 | 0.72917
2012-04-23 | IM | R | 15:00 | 17:00 | 2:00 | 2 | 2 | 3 | 2 | 2 |  | 1 | 1 | 13 | 1899-12-31 02:00
TOTALS |  |  |  |  | 100.3333 | 36 | 35 | 18 | 28 | 12 | 3 | 5 | 4 | 141 | 698
|  | SD | RA | CD | IM | Total
Total Hrs Mtg W |  | 9 | 201.6667 | 156.9167 | 127.1667 | 494.75
Total Hrs Mtg R |  | 12.75 | 138 | 26.5 | 26 | 203.25
Total Project Hrs |  | 21.75 | 339.6667 | 183.4167 | 153.1667 | 698
Formulas:
Total Labor Hrs = [Meeting Length]*[Total Labor]
=SUMIFS($Q$3:$Q$20,$B$3:$B$20,"SD",$C$3:$C$20,"W")*24
=SUM(F3:F20)*24
=SUM(P3:P20)*24
**must multiply by 24 for hrs > 1 day
**format start/end times as hh:mm & cells with sums as numbers

## Answers 12 c & d
Systems Development Labor Costs and Hours
Date | Project Phase | Meeting Type | Start Time | End Time | Meeting Length | Users |  | SAs |  | Prgms |  | PQAs |  | Lvl-2 User Mgr |  | Lvl-2 User Mgr |  | Lvl-2 IS Mgr |  | Lvl-2 IS Mgr |  | Total Labor
[6 empty] | Count | Hrs | Count | Hrs | Count | Hrs | Count | Hrs | Count | Hrs | Count | Hrs | Count | Hrs | Count | Hrs | Count | Hrs
2012-03-05 | SD | W | 20:35 | 22:05 | 0.0625 | 2 | 0.125 | 2 | 0.125 |  | 0 |  | 0 | 2 | 0.125 |  | 0 |  | 0 |  | 0 | 6 | 9:00
2012-03-07 | SD | R | 14:00 | 15:25 | 0.059028 | 3 | 0.1875 | 2 | 0.125 |  | 0 |  | 0 | 2 | 0.125 | 1 | 0.0625 | 1 | 0.0625 |  | 0 | 9 | 13:30
2012-03-24 | RA | W | 9:00 | 22:30 | 0.5625 | 3 | 0.1875 | 2 | 0.125 |  | 0 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 10:30
2012-03-27 | RA | W | 8:00 | 20:25 | 0.51736 | 2 | 0.125 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 6:00
2012-03-28 | RA | W | 8:30 | 20:00 | 0.47917 | 2 | 0.125 | 1 | 0.0625 |  | 0 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 5 | 7:30
2012-03-25 | RA | R | 9:00 | 20:30 | 0.47917 | 3 | 0.1875 | 2 | 0.125 |  | 0 | 2 | 0.125 | 2 | 0.125 | 1 | 0.0625 | 1 | 0.0625 | 1 | 0.0625 | 12 | 18:00
2012-03-28 | CD | W | 8:00 | 20:00 | 0.5 | 2 | 0.125 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 6:00
2012-03-30 | CD | W | 14:00 | 15:30 | 0.0625 | 2 | 0.125 | 2 | 0.125 |  | 0 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 9:00
2012-04-03 | CD | R | 16:00 | 17:00 | 0.041667 | 2 | 0.125 | 2 | 0.125 |  | 0 | 2 | 0.125 | 2 | 0.125 |  | 0 | 1 | 0.0625 | 1 | 0.0625 | 10 | 15:00
2012-04-05 | CD | W | 14:30 | 15:25 | 0.038194 | 2 | 0.125 | 2 | 0.125 |  | 0 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 6 | 9:00
2012-04-07 | CD | W | 9:25 | 20:45 | 0.47222 | 3 | 0.1875 | 3 | 0.1875 |  | 0 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 12:00
2012-04-09 | CD | W | 14:00 | 14:25 | 0.017361 | 3 | 0.1875 | 2 | 0.125 | 2 | 0.125 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 13:30
2012-04-20 | CD | R | 15:30 | 17:00 | 0.0625 | 3 | 0.1875 | 1 | 0.0625 |  | 0 | 2 | 0.125 | 2 | 0.125 | 1 | 0.0625 | 1 | 0.0625 | 1 | 0.0625 | 11 | 16:30
2012-04-22 | IM | W | 9:00 | 22:25 | 0.55903 |  | 0 | 2 | 0.125 | 3 | 0.1875 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 10:30
2012-04-25 | IM | W | 22:00 | 22:25 | 0.017361 | 2 | 0.125 | 2 | 0.125 | 3 | 0.1875 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 9 | 13:30
2012-04-26 | IM | W | 16:30 | 18:00 | 0.0625 |  | 0 | 2 | 0.125 | 4 | 0.25 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 8 | 12:00
2012-04-22 | IM | W | 14:00 | 16:30 | 0.10417 |  | 0 | 2 | 0.125 | 3 | 0.1875 | 2 | 0.125 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 10:30
2012-04-23 | IM | R | 15:00 | 17:00 | 0.083333 | 2 | 0.125 | 2 | 0.125 | 3 | 0.1875 | 2 | 0.125 | 2 | 0.125 |  | 0 | 1 | 0.0625 | 1 | 0.0625 | 13 | 19:30
TOTALS |  |  |  |  | 100.3333 | 36 | 54 | 35 | 52.5 | 18 | 27 | 28 | 42 | 12 | 18 | 3 | 4.5 | 5 | 7.5 | 4 | 6 | 141 | 211.5
Actual Costs and Hours of Development
[6 empty] | Users |  | SAs |  | Prgms |  | PQAs |  | Lvl-2 User Mgr |  | Lvl-2 User Mgr |  | Lvl-2 IS Mgr |  | Lvl-2 IS Mgr |  | Total
[5 empty] | Cost Per Hour | 35 |  | 43 |  | 38 |  | 40 |  | 58 |  | 47 |  | 56 |  | 47 |  | 364
[6 empty] | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs
[5 empty] | Actual SD | 262.5 | 0.3125 | 258 | 0.25 | 0 | 0 | 0 | 0 | 348 | 0.25 | 70.5 | 0.0625 | 84 | 0.0625 | 0 | 0 | 1023 | 0.9375
[5 empty] | Actual RA | 525 | 0.625 | 451.5 | 0.4375 | 0 | 0 | 360 | 0.375 | 174 | 0.125 | 70.5 | 0.0625 | 84 | 0.0625 | 70.5 | 0.0625 | 1735.5 | 1899-12-31 18:00
[5 empty] | Actual CD | 892.5 | 1899-12-31 01:30 | 903 | 0.875 | 114 | 0.125 | 720 | 0.75 | 348 | 0.25 | 70.5 | 0.0625 | 168 | 0.125 | 141 | 0.125 | 3357 | 1900-01-02 09:00
[5 empty] | Actual IM | 210 | 0.25 | 645 | 0.625 | 912 | 1899-12-31 | 600 | 0.625 | 174 | 0.125 | 0 | 0 | 84 | 0.0625 | 70.5 | 0.0625 | 2695.5 | 1900-01-01 18:00
[5 empty] | Actual Totals | 1890 | 54 | 2257.5 | 52.5 | 1026 | 27 | 1680 | 42 | 1044 | 18 | 211.5 | 4.5 | 420 | 7.5 | 282 | 6 | 8811 | 1900-01-07 19:30
Budgeted Costs and Hours of Development
[6 empty] | Users |  | SAs |  | Prgms |  | PQAs |  | Lvl-2 User Mgr |  | Lvl-2 User Mgr |  | Lvl-2 IS Mgr |  | Lvl-2 IS Mgr |  | Total
[5 empty] | Cost Per Hour | 35 |  | 43 |  | 38 |  | 40 |  | 58 |  | 47 |  | 56 |  | 47 |  | 364
[6 empty] | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs
[5 empty] | Budgeted SD | 350 | 0.41667 | 430 | 0.41667 | 0 | 0 | 0 | 0 | 348 | 0.25 | 188 | 0.16667 | 336 | 0.25 | 188 | 0.16667 | 1840 | 1899-12-31 16:00
[5 empty] | Budgeted RA | 350 | 0.41667 | 516 | 0.5 | 0 | 0 | 200 | 0.20833 | 232 | 0.16667 | 94 | 0.083333 | 112 | 0.083333 | 47 | 0.041667 | 1551 | 1899-12-31 12:00
[5 empty] | Budgeted CD | 525 | 0.625 | 645 | 0.625 | 190 | 0.20833 | 480 | 0.5 | 232 | 0.16667 | 47 | 0.041667 | 112 | 0.083333 | 47 | 0.041667 | 2278 | 1900-01-01 07:00
[5 empty] | Budgeted IM | 140 | 0.16667 | 344 | 0.33333 | 570 | 0.625 | 480 | 0.5 | 116 | 0.083333 | 0 | 0 | 112 | 0.083333 | 0 | 0 | 1762 | 1899-12-31 19:00
[5 empty] | Budgeted Totals | 32760 | 39 | 1935 | 45 | 760 | 20 | 1160 | 29 | 928 | 16 | 329 | 7 | 672 | 12 | 282 | 6 | 7431 | 1900-01-06 06:00
Variance in Costs and Hours of Development
[6 empty] | Users |  | SAs |  | Prgms |  | PQAs |  | Lvl-2 User Mgr |  | Lvl-2 User Mgr |  | Lvl-2 IS Mgr |  | Lvl-2 IS Mgr |  | Total
[5 empty] | Cost Per Hour | 35 |  | 43 |  | 38 |  | 40 |  | 58 |  | 47 |  | 56 |  | 47 |  | 364
[6 empty] | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs | Costs | Hrs
[5 empty] | Variance SD | 87.5 | 2.5 | 172 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 117.5 | 2.5 | 252 | 4.5 | 188 | 4 | 817 | 17.5
[5 empty] | Variance RA | -175 | -5 | 64.5 | 1.5 | 0 | 0 | -160 | -4 | 58 | 1 | 23.5 | 0.5 | 28 | 0.5 | -23.5 | -0.5 | -184.5 | -6
[5 empty] | Variance CD | -367.5 | -10.5 | -258 | -6 | 76 | 2 | -240 | -6 | -116 | -2 | -23.5 | -0.5 | -56 | -1 | -94 | -2 | -1079 | -26
[5 empty] | Variance IM | -70 | -2 | -301 | -7 | -342 | -9 | -120 | -3 | -58 | -1 | 0 | 0 | 28 | 0.5 | -70.5 | -1.5 | -933.5 | -23
[5 empty] | Variance Totals | -525 | -15 | -322.5 | -7.5 | -266 | -7 | -520 | -13 | -116 | -2 | 117.5 | 2.5 | 252 | 4.5 | 0 | 0 | -1380 | -37.5
Formulas:
Hrs = SUM([Users]*F4)
Hrs = SUM([SAs]*F4)
=SUM(H4:H21)*24
=SUM(R4:R21)*24
**must multiply by 24 when using hrs
**format times as hh:mm & the cells with sums as numbers
=SUMIF($B$4:$B$21,"SD",H4:H21)
=SUM(G$25*H27)*24
=SUM(G5*$F$4)
=SUM(G36-G27)
=SUM(H38-H29)*24