Request for funding for research showing

Online Learning is more effective

Than lecture based learning

- Project description:

At the University of Houston, certain classes are given through an online program. These classes are less expensive and make it easier for students to maintain their school work as well as outside activities and jobs because it gives them the possibility to work from home when the time is convenient for them. Many students are unaware of this, or do not think that taking online classes will be beneficial to them, but I believe that not only will it be beneficial for students who have to work while going to University, it will give the opportunity to others who may not have the financial requirements to obtain a degree and get the same chance as those who attend in class lectures. For this reason I would like to apply for a grant to fund a project that will require:

- 50 students

- 1 professor for lectures on a certain topic (biology)

- Access to the online course of biology at U of H for 25 students

- Timeline and Schedule for appraisal:

| Start Date | End Date |
| --- | --- |
| School begins January 7th 2015, 25 of the students placed in lectures, 25 in the online program of the University. | School ends May 7th 2015, grades are distributed for the 50 students. |
| Government pays for kids tuitions before school begins | Government pays for exams at the end of the term |
| May 7th begin comparing how well the students in the online program did compared to those attending lectures | By May 30th have all the data collected, revised, and printed. |

- Budget:

Approximately 5,000USD for the students attending lectures, 3,750USD for those doing the online program, 3,000USD for the professor hired. Total of 11,750USD

- Potential Value of project:

This project will not only be beneficial economically for students because they will be able to maintain their school work with outside work, but for the University as well. Less professors will have to be hired which will cost less, and eventually give the University the possibility of lowering tuition which ought to increase the number of students having the opportunity to attend University and obtain a degree.