Phase I : Initiating and Establishing the Effort (Months 1-4)

- Securing support of local chief executive and administrative leaders

- Recruiting community and government agency partners

- Generating public enthusiasm through immediate action and publicity for results

- Training coalition members in the planning process and content issues

Phase II : Developing the Strategic Approach (Months 4-10)

- Creating a vision

- Defining structure, organizing the process, and securing staff support

- Assessing community issues and priorities

- Formulating goals and objectives

- Establishing measures of success and how the initiative will track progress

- Developing a strategic, comprehensive plan to address priorities

- Identifying and recruiting resources needed to get the job done

- Recognizing key partners contribution

- Publishing and publicizing the plan

Phase III : Implementing and Sustaining the Comprehensive Approach (Months 10-15)

- Setting up for implementation

- Getting help in implementing

- Evaluating the impact of the strategy

- Revising the objectives, success measures, and operational strategy as necessary to support