Which of the following is used to compute the earliest finish times once the earliest start times are calculated for activities on a precedence network?

Select one:

a. variance in project duration

b. activities that are on the critical path

c. activity slack time

d. expected project duration

e. maximum project duration

#### Feedback

The correct answer is: expected project duration

### Question 2

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Given this network:

  
 
The critical path for the network shown is:

Select one:

a. a-d-h-i

b. b-e-f-g

c. b-e-h-i

d. a-c-g

e. a-d-f-g

#### Feedback

The correct answer is: b-e-f-g

### Question 3

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Scheduling, execution and control decision are usually __________ and __________ term.

Select one:

a. strategic; long

b. operational; short

c. operational; long

d. system design; medium

e. forecasting; short

#### Feedback

The correct answer is: operational; short

### Question 4

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

A company has introduced a process improvement that reduces processing time for each unit, so that output is increased by 25% with less material, but one additional worker required. Under the old process, five workers could produce 60 units per hour. Labour costs are $12/hour, and material input was previously $16/unit. For the new process, material is now $10/unit. Overhead is charged at 1.6 times direct labour cost. Finished units sell for $31 each. What is the productivity AFTER the process improvement (in $ of output / $ of input)?

Select one:

a. 1.913

b. 1.667

c. None of the given choices

d. 2.481

e. 2.571

#### Feedback

The correct answer is: 2.481

### Question 5

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

A popular tool for planning and scheduling simple projects is the:

Select one:

a. program evaluation and review technique

b. critical path method

c. Gantt chart

d. activity-on-nodes network

e. activity-on-arrows network

#### Feedback

The correct answer is: Gantt chart

A project manager for Durable Construction Co. is about to build a house involving the following six activities:

  
 
What is the estimated expected (mean) duration for project completion?

Select one:

a. 300 days

b. 170 days

c. 200 days

d. 210 days

e. 160 days

#### Feedback

The correct answer is: 200 days

### Question 7

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Activity 7 is directly preceded by two activities—activity 5 and activity 6. Activity 5 has an expected duration of five and an ES time of six. Activity 6 has an expected duration of seven and an ES time of seven. Activity 7 has an expected duration of 10. The ES for activity 7 is:

Select one:

a. 21

b. 11

c. 14

d. 24

e. 25

#### Feedback

The correct answer is: 14

### Question 8

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Which of the following is not involved in project planning?

Select one:

a. Quality planning

b. Risk management planning

c. Communication planning

d. Purchase planning

e. Capacity expansion planning

#### Feedback

The correct answer is: Capacity expansion planning

### Question 9

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Tactical operational activities involve making decisions about all of the following EXCEPT:

Select one:

a. project management

b. location of facilities

c. scheduling

d. inventory management

e. material requirements planning

#### Feedback

The correct answer is: location of facilities

### Question 10

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Given this network:

  
 
The expected duration of this project is:

Select one:

a. 77

b. 36

c. 12

d. 17

e. 20

#### Feedback

The correct answer is: 20

The Project Manager is about to begin a project comprised of the following six activities:

  
 
What is the estimated expected (mean) duration for project completion?

Select one:

a. 140 days

b. 100 days

c. 200 days

d. 199 days

e. 440 days

#### Feedback

The correct answer is: 200 days

### Question 12

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

If two consecutive activities on the same path each have two days of activity slack, this means that:

Select one:

a. None of the given choices

b. Each of them could use half of the slack without delaying the completion of the project

c. Additional resources should be allocated to these two activities

d. Both activities are on the critical path

e. Each of them can be delayed by two days without delaying the completion of the project

#### Feedback

The correct answer is: Each of them could use half of the slack without delaying the completion of the project

### Question 13

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

A project manager for Durable Construction Co. is about to build a house involving the following six activities:

  
 
What is the probability that the critical path for this project will be completed within 210 days?

Select one:

a. 0.9987

b. 0.5000

c. 0.9772

d. 0.8413

e. 0.9544

#### Feedback

The correct answer is: 0.9772

### Question 14

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

The Project Manager is about to begin a project comprised of the following six activities:

  
 
What is the estimated standard deviation of the duration for activity E?

Select one:

a. 16 days

b. 4 days

c. 24 days

d. 3 days

e. 2 days

#### Feedback

The correct answer is: 4 days

### Question 15

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

A project manager for Durable Construction Co. is about to build a house involving the following six activities:

  
 
What is the estimated expected (mean) duration for activity E?

Select one:

a. 39 days

b. 40 days

c. 45 days

d. 35 days

e. 36 days

#### Feedback

The correct answer is: 35 days

Which of the following are advantages of CPM/PERT?

I. Relationships among activities can be identified.
II. It is automatically updated.
III. Activities that need to be watched closely can be identified.

Select one:

a. I and II

b. I, II, and III

c. I and III

d. III only

e. II and III

#### Feedback

The correct answer is: I and III

### Question 17

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

The Project Manager is about to begin a project comprised of the following six activities:

  
 
What is the estimated slack time for the path A-D-F?

Select one:

a. 40 days

b. 20 days

c. 60 days

d. 0 days

e. 100 days

#### Feedback

The correct answer is: 60 days

### Question 18

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Characteristics that customers perceive as minimum standards of acceptability are called:

Select one:

a. Minimum attributes

b. Order qualifiers

c. Core competencies

d. Order winners

e. Distinctive competencies

#### Feedback

The correct answer is: Order qualifiers

### Question 19

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

Measuring process outputs at various points in order to compare outputs to previously established standards to determine if corrective action is needed is called:

Select one:

a. directing and conversion

b. feedback and control

c. planning and directing

d. leading and transformation

e. controlling and leading

#### Feedback

The correct answer is: feedback and control

### Question 20

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

In precedence network analysis, knowing the slack time allows managers to:

I) allocate scarce resources
II) pay attention to activities that could delay the project
III) delay critical activities

Select one:

a. I only

b. I and II only

c. I, II, and III

d. III only

e. II only

#### Feedback

The correct answer is: I and II only

There are four activities on the critical path, and they have standard deviations of 1, 2, 4, and 2 days. The standard deviation of the critical path is:

Select one:

a. 25

b. 5

c. 3

d. 9

e. 16

#### Feedback

The correct answer is: 5

### Question 22

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

A project manager for Durable Construction Co. is about to build a house involving the following six activities:

  
 
What is the estimated standard deviation of the duration for activity E?

Select one:

a. 5 days

b. 4 days

c. 2 days

d. 3 days

e. 1 day

#### Feedback

The correct answer is: 2 days

### Question 23

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

The Project Manager is about to begin a project comprised of the following six activities:

  
 
What is the estimated expected (mean) duration for activity E?

Select one:

a. 100 days

b. 91 days

c. 101 days

d. 115 days

e. 99 days

#### Feedback

The correct answer is: 101 days

### Question 24

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

The practice of buying a part of a good/service or a segment of production/service processes from another company is a tactic associated with what generic operations strategy?

Select one:

a. Low labour cost strategy

b. Scale-based strategy

c. Outsourcing

d. Focused factories strategy

e. Flexible factories strategy

#### Feedback

The correct answer is: Outsourcing

### Question 25

Correct

Mark 1.00 out of 1.00

Flag question

#### Question text

When developing probabilistic estimates of project duration, it is necessary to know which of the following?

Select one:

a. the distribution of activity durations

b. the mean and variance of every activity

c. the mean and variance of activities on the critical path

d. each activity's probability of completion

e. the standard deviation of activities on the critical path

#### Feedback

The correct answer is: the mean and variance of every activity

Which of the following is not an advantage to using project management software?

Select one:

a. It reduces project costs.

b. It can enhance communication among team members.

c. It provides a logical planning structure.

d. It can generate various charts.

e. It automatically generates and formats a variety of reports.

#### Feedback

The correct answer is: It reduces project costs.

### Question 27

Correct

Mark 1.00 out of 1.00

#### Question text

A project manager for Durable Construction Co. is about to build a house involving the following six activities:

  
 
What is the estimated slack time for the path B-D-F?

Select one:

a. 0 days

b. 50 days

c. 30 days

d. 40 days

e. 100 days

#### Feedback

The correct answer is: 30 days

### Question 28

Correct

Mark 1.00 out of 1.00

#### Question text

Given the portion of the network shown above, what is the earliest finish time for activity D, if the earliest start time of B is 12, and the earliest start time of C is 13?

Select one:

a. 19

b. 20

c. 23

d. 21

e. 22

#### Feedback

The correct answer is: 23

### Question 29

Correct

Mark 1.00 out of 1.00

#### Question text

Which of the following is not a form of risk reduction in project management?

Select one:

a. backup systems

b. Improving communications

c. outsourcing components of the project

d. expand the project scope to reduce external dependencies

e. frequent monitoring of project activities

#### Feedback

The correct answer is: expand the project scope to reduce external dependencies

### Question 30

Correct

Mark 1.00 out of 1.00

#### Question text

Given this information about activity B: ES = 10, EF = 15, LS = 16, and LF = 21, we can determine that the amount of slack associated with the activity is:

Select one:

a. 0

b. 5

c. 11

d. 1

e. 6

#### Feedback

The correct answer is: 6