Chapter 17 Project Management

| 1. | Projects involve routine activities that are performed repeatedly. True False |
| --- | --- |

| 2. | One way that project management differs from management of more traditional activities is the limited life-time of projects. True False |
| --- | --- |

| 3. | Once a project is underway, project managers are only responsible for effectively managing time and costs. True False |
| --- | --- |

| 4. | Projects typically go through a life cycle. True False |
| --- | --- |

| 5. | Some organizations use a matrix organization to integrate the activities of specialists within a functional framework. True False |
| --- | --- |

| 6. | A project manager usually staffs the human resources required for a project by hiring outside specialists that only work for the company for the duration of the project. True False |
| --- | --- |

| 7. | Project managers must often function in an environment that is beset with uncertainties. True False |
| --- | --- |

| 8. | The probability of occurrence of risk events is lower near the beginning of a project and higher near the end of the project. True False |
| --- | --- |

| 9. | The costs associated with risk events tend to be lower near the beginning of a project, and higher near the end of the project. True False |
| --- | --- |

| 10. | The task of identifying risks should involve everyone associated with the project. True False |
| --- | --- |

| 11. | A list of risks and other key information collected as part of risk management planning is stored in a risk register. True False |
| --- | --- |

| 12. | Risks involved in a project can be transferred by outsourcing a particular component of the project and requiring performance bonds. True False |
| --- | --- |

| 13. | A hierarchical listing of what must be done during a project is called matrix. True False |
| --- | --- |

| 14. | An advantage of Gantt charts in project management is that they reveal which activities can be delayed without delaying the overall project. True False |
| --- | --- |

| 15. | A Gantt chart reveals the sequence of activities in a project. True False |
| --- | --- |

| 16. | A Gantt chart can be a useful tool for simple projects. True False |
| --- | --- |

| 17. | Although PERT and CPM were originally developed for somewhat different types of projects, they are now nearly identical in terms of analysis and procedures. True False |
| --- | --- |

| 18. | PERT was originally developed for projects that had high levels of uncertainty. True False |
| --- | --- |

| 19. | The precedence network for a project describes sequential relationships among major activities in a project. True False |
| --- | --- |

| 20. | The path in a PERT/CPM precedence network with the fewest activities is referred to as the critical path. True False |
| --- | --- |

| 21. | The path in a precedence network with the shortest duration is the critical path. True False |
| --- | --- |

| 22. | The sum of activity durations of the longest path in a network indicates expected project completion time, and the activities on it are called the critical activities. True False |
| --- | --- |

| 23. | The critical path has zero path slack time. True False |
| --- | --- |

| 24. | The earliest finish time for an activity is equal to the latest finish time minus the activity time. True False |
| --- | --- |

| 25. | The latest starting time for an activity is equal to the latest finish time minus the activity time. True False |
| --- | --- |

| 26. | The earliest finish time for an activity is equal to the latest finish time minus the activity slack. True False |
| --- | --- |

| 27. | Activity slack is the difference between the latest finish and earliest finish times. True False |
| --- | --- |

| 28. | Activities not on the critical path have a slack time equal to zero. True False |
| --- | --- |

| 29. | If two consecutive activities on the same path each have two days of activity slack, this means that each of them can be delayed by two days without delaying the project. True False |
| --- | --- |

| 30. | If two consecutive activities on the same path have shared slack, this means that each of them could use half of the slack without delaying completion of the project. True False |
| --- | --- |

| 31. | Deterministic networks use three duration estimates for each activity in order to best determine the activity's estimated duration. True False |
| --- | --- |

| 32. | A normal distribution is usually used to describe probabilistic duration estimates for activities in a project. True False |
| --- | --- |

| 33. | A beta distribution is generally used to describe probabilistic project duration. True False |
| --- | --- |

| 34. | The variance of project duration is equal to the sum of the variances of all the activities of the project. True False |
| --- | --- |

| 35. | The standard deviation of the critical path is equal to the square root of the sum of the variances of all of the activities on the critical path. True False |
| --- | --- |

| 36. | If the expected length of a path is more than 2.5 standard deviations less than a desired project completion time, the path would not be a factor in assessing the probability of finishing the project on time. True False |
| --- | --- |

| 37. | In order to determine the probability of timely project completion, it is sometimes necessary to take into account paths other than the critical path. True False |
| --- | --- |

| 38. | The probability that the project will go beyond the desired time is equal to one minus the joint probability that all paths will be completed within the desired time. True False |
| --- | --- |

| 39. | Simulation can be used for cases in which network activity durations are dependent. True False |
| --- | --- |

| 40. | Project managers are sometimes able to reduce indirect project costs by increasing direct costs. True False |
| --- | --- |

| 41. | Only activities on the critical path are initial candidates for crashing. True False |
| --- | --- |

| 42. | The optimum project length in crashing occurs where the cumulative cost of crashing equals savings in the indirect costs. True False |
| --- | --- |

| 43. | Scope creep refers to the tendency for projects to take longer than planned. True False |
| --- | --- |

| 44. | The cost control technique of earned value analysis measures project progress by the budgeted cost of work scheduled. True False |
| --- | --- |

| 45. | Which of the following would probably not involve the use of project management? A.; planning and constructing a new city hall. B.; developing an advertising campaign for a new product. C.; designing and constructing a subway system. D.; scheduling workers for a production plant. E.; preparing for the visit of a foreign dignitary. |
| --- | --- |

| 46. | The life cycle of a project includes which of the following phases: I) initiation II) planning and scheduling III) growth and maturity IV) closeout A.; I and II. B.; II and III. C.; I, II and IV. D.; II, III and IV. E.; I, II, III and IV. |
| --- | --- |

| 47. | Workers on a project are: A.; often on loan from their regular job. B.; often working only part-time on the project. C.; usually on the project for less than its full completion. D.; all of the choices. |
| --- | --- |

| 48. | Once a project is underway, the project manager is responsible for effectively managing: I) the people II) costs III) time A.; I. B.; II. C.; III. D.; I and II. E.; I, II and III. |
| --- | --- |

| 49. | Project planning involves all but which of the following? A.; Risk management planning. B.; Capacity expansion planning. C.; Quality planning. D.; Communication planning. E.; Purchase planning. |
| --- | --- |

| 50. | Risk avoidance can be done by all but which of the following actions? A.; Extending the schedule. B.; Reducing project scope. C.; Creating contingency funds. D.; Clarifying requirements. E.; All of these are risk avoidance actions. |
| --- | --- |

| 51. | Which of the following is not a form of risk reduction in project management? A.; backup systems. B.; outsourcing components of the project. C.; frequent monitoring of project activities. D.; expand the project scope to reduce external dependencies. E.; Improving communications. |
| --- | --- |

| 52. | A hierarchical listing of what must be done in a project is called: A.; work breakdown structure (WBS). B.; program evaluation and review technique (PERT). C.; planning matrix. D.; crashing. E.; critical path method (CPM). |
| --- | --- |

| 53. | The project management technique that is repeated until activities are decomposed into work packages that can be performed by a designated worker, team or subcontract is called: A.; work breakdown structure (WBS). B.; program evaluation and review technique (PERT). C.; planning matrix. D.; crashing. E.; none of the choices. |
| --- | --- |

| 54. | Which of the following is part of project scheduling? A.; identify resource requirements for activities. B.; activity duration estimates. C.; project crashing. D.; identify sequential dependencies among activities. E.; all the choices. |
| --- | --- |

| 55. | A popular tool for planning and scheduling simple projects is the: A.; activity-on-arrows network. B.; activity-on-nodes network. C.; Gantt chart. D.; critical path method. E.; program evaluation and review technique. |
| --- | --- |

| 56. | The advantage(s) a Gantt chart has over other project scheduling techniques is (are): A.; its ability to reveal relationships among activities. B.; it can easily show networks.. C.; (a) and (b). D.; its simplicity. E.; all of the choices. |
| --- | --- |

| 57. | The advantage(s) a precedence diagram has over a Gantt chart is (are): A.; its ability to reveal relationships among activities. B.; It can easily show networks.. C.; (a) and (b). D.; its simplicity. E.; all of the choices are correct.. |
| --- | --- |

| 58. | Besides project activities, the primary information that all Gantt charts illustrate is: A.; project budget and when activities occur. B.; cost of activities and delays in the schedule. C.; planned duration of activities and when they occur in the schedule. D.; project budget and staffing levels. E.; critical path and project budget. |
| --- | --- |

| 59. | Concerning PERT and CPM: A.; These are two different names for essentially the same technique.. B.; CPM tends to focus more on the critical path.. C.; PERT gives a clearer indication of activity slack, while CPM gives a better picture of path slack.. D.; Because of its recent discovery, much less is known about CPM than PERT.. E.; All of these are true.. |
| --- | --- |

| 60. | Which of the following are advantages of CPM/PERT? I. It is visual. II. It is automatically updated. III. Activities that need to be watched closely can be identified. A.; I and II. B.; II and III. C.; III only. D.; I and III. E.; I, II, and III. |
| --- | --- |

| 61. | In a precedence network the critical path is the sequence of activities which has: A.; the most activities. B.; the most nodes. C.; the most events. D.; the longest duration. E.; the greatest variance. |
| --- | --- |

| 62. | Given the portion of the network shown above, what is the earliest finish time for activity D, if the earliest start time of B is 12, and the earliest start time of C is 13? A.; 19. B.; 20. C.; 21. D.; 22. E.; 23. |
| --- | --- |

| 63. | Activity 7 is directly preceded by two activities—activity 5 and activity 6. Activity 5 has an expected duration of five and an ES time of six. Activity 6 has an expected duration of seven and an ES time of seven. Activity 7 has an expected duration of 10. The ES for activity 7 is: A.; 11. B.; 14. C.; 21. D.; 24. E.; 25. |
| --- | --- |

| 64. | Which of the following is used to compute the earliest finish times once the earliest start times are calculated for activities on a precedence network? A.; expected project duration. B.; activity slack time. C.; which activities are on the critical path. D.; variance in project duration. E.; maximum project duration. |
| --- | --- |

| 65. | Given the portion of the network shown above, what is the latest start time of activity 7 if the latest finish of activity 8 is 26, and the latest finish of activity 9 is 23? A.; 18. B.; 17. C.; 13. D.; 12. E.; 10. |
| --- | --- |

| 66. | An activity, A, has two succeeding activities, B and C. Given the following information, determine the latest starting time for activity A. EF B = 15, EF C = 17, LF B = 24, LF C = 27; activity times are A = 4, B = 6, C = 8. A.; 14. B.; 15. C.; 16. D.; 17. E.; 18. |
| --- | --- |

| 67. | Activity C has an early start time of 8, an early finish time of 12, a latest start time of 13, and a latest finish time of 17. Its slack is: A.; 0. B.; 1. C.; 4. D.; 5. E.; 9. |
| --- | --- |

| 68. | Given this information about activity B: ES = 10, EF = 15, LS = 16, and LF = 21, we can determine that the amount of slack associated with the activity is: A.; 0. B.; 1. C.; 5. D.; 6. E.; 11. |
| --- | --- |

| 69. | In precedence network analysis, knowing the slack time allows managers to: I) allocate scarce resources II) pay attention to activities that could delay the project III) delay critical activities A.; I. B.; II. C.; III. D.; I and II. E.; I, II and III. |
| --- | --- |

| 70. | In the probabilistic approach to precedence network analysis, the duration estimate annotated "tm" for any activity is the: A.; mean duration. B.; median duration. C.; most likely duration. D.; optimistic duration. E.; pessimistic duration. |
| --- | --- |

| 71. | In the probabilistic approach to precedence network analysis, the duration estimate that is given the highest weighting in calculating the expected duration for an activity is: A.; duration of the immediately prior activity. B.; duration of the immediately following activity. C.; most likely duration. D.; optimistic duration. E.; pessimistic duration. |
| --- | --- |

| 72. | When developing probabilistic estimates of project duration, it is necessary to know which of the following? A.; the mean and variance of every activity. B.; the mean and variance of activities on the critical path. C.; the standard deviation of activities on the critical path. D.; each activity's probability of completion. E.; the distribution of activity durations. |
| --- | --- |

| 73. | A PERT/CPM activity has an optimistic duration estimate of three days, a most likely duration estimate of eight days, and a pessimistic duration estimate of 10 days. The expected duration of this activity is: A.; 7.0. B.; 7.5. C.; 8.0. D.; 8.5. E.; 10.0. |
| --- | --- |

| 74. | Activity 4 in a network diagram has an optimistic duration estimate of five days, a most likely duration estimate of seven days, and a pessimistic duration estimate of 10 days. Its expected duration is approximately: A.; 5. B.; 6. C.; 7. D.; 8. E.; 9. |
| --- | --- |

| 75. | There are four activities on the critical path, and they have standard deviations of 1, 2, 4, and 2 days. The standard deviation of the critical path is: A.; 3. B.; 5. C.; 9. D.; 16. E.; 25. |
| --- | --- |

| 76. | There are four activities on the critical path. Coincidentally, their standard deviations are all equal to 4. The standard deviation of the critical path is therefore equal to: A.; 2. B.; 4. C.; 8. D.; 16. E.; 64. |
| --- | --- |

| 77. | The project management strategy of injecting additional resources in order to reduce the length of the project is called: A.; expediting. B.; rushing. C.; panicking. D.; crashing. E.; none of the choices are correct.. |
| --- | --- |

| 78. | In "crashing" a project, a manager will generally focus on activities which: A.; are not on the critical path. B.; are the least costly to crash. C.; are costly to crash and are on the critical path. D.; are on the critical path and are the least costly to crash. E.; none of the choices are correct.. |
| --- | --- |

| 79. | At which point does crashing of a project cease? A.; when the project is completed. B.; when no additional crashing is possible. C.; when the cost to crash equals or exceeds the benefit of crashing. D.; all of the choices. E.; none of the choices. |
| --- | --- |

| 80. | Uncontrolled growth in the number of activities that end up being included as part of a project is called: A.; the critical path. B.; project slack. C.; scope creep. D.; indirect costs. E.; time-cost-tradeoffs. |
| --- | --- |

| 81. | Which of the following is not an advantage to using project management software? A.; It automatically generates and formats a variety of reports.. B.; It reduces project costs.. C.; It can enhance communication among team members.. D.; It can generate various charts.. E.; It provides a logical planning structure.. |
| --- | --- |

|  | Given this network. |
| --- | --- |

| 82. | The expected duration of this project is: A.; 12. B.; 17. C.; 20. D.; 36. E.; 77. |
| --- | --- |

| 83. | The critical path for the network shown is: A.; a-c-g. B.; a-d-f-g. C.; a-d-h-i. D.; b-e-f-g. E.; b-e-h-i. |
| --- | --- |

|  | Given this network. |
| --- | --- |

| 84. | The expected duration of this project is: A.; 11. B.; 19. C.; 20. D.; 36. E.; 86. |
| --- | --- |

| 85. | The critical path for the network shown is: A.; 1-2-6-7. B.; 1-2-4-7. C.; 1-4-7. D.; 1-3-4-7. E.; 1-3-5-7. |
| --- | --- |

|  | The Project Manager is about to begin a project comprised of the following six activities: |
| --- | --- |

| 86. | What is the estimated expected (mean) duration for activity E? A.; 91 days. B.; 99 days. C.; 100 days. D.; 101 days. E.; 115 days. |
| --- | --- |

| 87. | What is the estimated standard deviation of the duration for activity E? A.; 2 days. B.; 3 days. C.; 4 days. D.; 16 days. E.; 24 days. |
| --- | --- |

| 88. | What is the estimated expected (mean) duration for project completion? A.; 100 days. B.; 140 days. C.; 199 days. D.; 200 days. E.; 440 days. |
| --- | --- |

| 89. | What is the estimated slack time for activity A? A.; 0 days. B.; 20 days. C.; 40 days. D.; 60 days. E.; 100 days. |
| --- | --- |

| 90. | What is the probability that this project will be completed within 205 days? A.; 0.6826. B.; 0.8413. C.; 0.9544. D.; 0.9772. E.; 0.9987. |
| --- | --- |

|  | The owner of Ace Building Co. is about to begin work on a project comprised of the following four activities: |
| --- | --- |

| 91. | What is the estimated expected (mean) duration for activity D? A.; 32 days. B.; 41 days. C.; 44 days. D.; 42 days. E.; 40 days. |
| --- | --- |

| 92. | What is the estimated standard deviation of the duration for activity D? A.; 0 days. B.; 2 days. C.; 3 days. D.; 4 days. E.; 12 days. |
| --- | --- |

| 93. | What is the estimated expected (mean) duration for project completion? A.; 41 days. B.; 70 days. C.; 100 days. D.; 120 days. E.; 221 days. |
| --- | --- |

| 94. | What is the estimated slack time for activity D? A.; 0 days. B.; 19 days. C.; 20 days. D.; 79 days. E.; 80 days. |
| --- | --- |

| 95. | What is the probability that this project will be completed within 130 days? A.; .8413. B.; .90. C.; .9544. D.; .9772. E.; .9987. |
| --- | --- |

|  | A project manager for Durable Construction Co. is about to build a house involving the following six activities: |
| --- | --- |

| 96. | What is the estimated expected (mean) duration for activity E? A.; 35 days. B.; 36 days. C.; 39 days. D.; 40 days. E.; 45 days. |
| --- | --- |

| 97. | What is the estimated standard deviation of the duration for activity E? A.; 1 days. B.; 2 days. C.; 3 days. D.; 4 days. E.; 5 days. |
| --- | --- |

| 98. | What is the estimated expected (mean) duration for project completion? A.; 160 days. B.; 170 days. C.; 200 days. D.; 210 days. E.; 300 days. |
| --- | --- |

| 99. | What is the estimated slack time for activity D? A.; 0 days. B.; 30 days. C.; 40 days. D.; 50 days. E.; 100 days. |
| --- | --- |

| 100. | What is the probability that the critical path for this project will be completed within 210 days? A.; 0.5000. B.; 0.8413. C.; 0.9544. D.; 0.9772. E.; 0.9987. |
| --- | --- |

|  | A project superintendent is about to begin work on a freeway resurfacing project, which is comprised of the following five activities: |
| --- | --- |

| 101. | What is the estimated expected (mean) duration for Activity E? A.; 31 weeks. B.; 38 weeks. C.; 39 weeks. D.; 40 weeks. E.; 43 weeks. |
| --- | --- |

| 102. | What is the estimated standard deviation of the duration for activity E? A.; 0 weeks. B.; 1 week. C.; 2 weeks. D.; 3 weeks. E.; 4 weeks. |
| --- | --- |

| 103. | What is the estimated expected (mean) duration for project completion? A.; 35 weeks. B.; 39 weeks. C.; 50 weeks. D.; 104 weeks. E.; 105 weeks. |
| --- | --- |

| 104. | What is the estimated slack time for Activity E? A.; 0 weeks. B.; 3 weeks. C.; 9 weeks. D.; 11 weeks. E.; 12 weeks. |
| --- | --- |

| 105. | What is the probability that the critical path for this project will be completed within 52 weeks? A.; 0.1554. B.; 0.3108. C.; 0.3466. D.; 0.6554. E.; 0.8277. |
| --- | --- |

|  | The manager of a National Forest is about to undertake a reforestation project in a burned out area. The project will involve the following six activities: |
| --- | --- |

| 106. | What is the estimated expected (mean) duration for activity Y? A.; 30 days. B.; 29 days. C.; 38 days. D.; 26 days. E.; 35 days. |
| --- | --- |

| 107. | What is the estimated standard deviation of the duration for activity Z? A.; 3 days. B.; 2 days. C.; 4 days. D.; 8 days. E.; 5 days. |
| --- | --- |

| 108. | What is the estimated expected (mean) duration for project completion? A.; 135 days. B.; 145 days. C.; 170 days. D.; 180 days. E.; 255 days. |
| --- | --- |

| 109. | What is the estimated slack time for activity W? A.; 0 days. B.; 25 days. C.; 35 days. D.; 45 days. E.; 85 days. |
| --- | --- |

| 110. | What is the probability that the critical path for this project will be completed within 200 days? A.; 0.8413. B.; 0.9544.. C.; 0.9772. D.; 0.9974. E.; 0.9987. |
| --- | --- |

| 111. | Assume that you are the manager of the project described above. What probability would you assign to a project duration of more than 8.5 weeks? |
| --- | --- |

| 112. | Using the information given, do the following: (i) Draw the precedence network diagram. (ii) Identify the critical path. (iii) Determine expected project duration. |
| --- | --- |

| 113. | Given the network diagram above, determine each of the following: (i) the activities which are on the critical path (ii) the expected project duration (iii) the probability that the project will be completed in 29 weeks or less (Note: the numbers on each node refers to the expected duration and standard deviation in weeks for that activity. E.G., 8,2 indicates an expected duration of eight and a standard deviation of two weeks.) |
| --- | --- |

| 114. | Determine the amount of slack in each of a project's activities (see the list below), and identify those which are on the critical path. |
| --- | --- |

| 115. | Given the network diagram, determine the probability that the project will finish within 19 weeks of its start. Durations on the diagram are in weeks. |
| --- | --- |

| 116. | A project consists of nine major activities, as shown. There are three separate paths in the network: a-c-f, b-d-g, and e-h-i. (i) What is expected project duration time? (ii) Determine the probability that the project will take more than 35 weeks to complete. (All durations are in weeks.) |
| --- | --- |

| 117. | Activity E has an optimistic duration of 9 days, a most likely duration of 12 days, and a pessimistic duration of 15 days. Estimate its expected duration and standard deviation. |
| --- | --- |

| 118. | A project has the activities and activity durations (days) listed below. There are two paths: start-A-B-end and start-C-D-finish. Determine the probability that the project will require more than 15 days from start to finish. |
| --- | --- |

| 119. | Activity D has an optimistic duration of 3 days, a pessimistic duration of 9 days, and a most likely duration of 4 days. Determine its expected duration and variance. |
| --- | --- |

| 120. | What is the probability that this project will take more than 10 weeks to complete if the mean and standard deviations activity durations and the network diagram are as shown below: |
| --- | --- |

| 121. | What are the estimated expected (mean) durations (in weeks) for activities A-H? |
| --- | --- |

| 122. | What are the estimated standard deviations (in weeks) of the durations for activities A-H? |
| --- | --- |

| 123. | What is the estimated expected (mean) duration (in weeks) for project completion? |
| --- | --- |

| 124. | What are the estimated slack times (in weeks) for activities A-H? |
| --- | --- |

| 125. | What is the critical path for this project network? |
| --- | --- |

| 126. | What is the estimated standard deviation (in weeks) for the critical path completion time? |
| --- | --- |

| 127. | What is the probability that the critical path for this project will be completed within 75 weeks? 80 weeks? 85 weeks? 90 weeks? |
| --- | --- |

| 128. | Within what amount of time (in weeks) is there a 90% probability that the critical path for this project will be completed? 95%? 99%? |
| --- | --- |

| 129. | What activities make up the critical path? |
| --- | --- |

| 130. | In crashing this project, which activity is the first to be reduced? |
| --- | --- |

| 131. | In crashing this project to 18 weeks, which activities (in order of selection) will be reduced? |
| --- | --- |

| 132. | What is the total cost of reducing this project by two weeks? |
| --- | --- |

| 133. | What is the total cost of reducing the project to 18 weeks? |
| --- | --- |

| 134. | Indirect cost for a project is $2500 per day. Given the following information, determine an optimum crashing plan. What is the total cost for the plan? |
| --- | --- |

Chapter 17 Project Management Key

| 1. | Projects involve routine activities that are performed repeatedly. FALSE |
| --- | --- |

Difficulty: Easy Learning Objective: 1 Stevenson - Chapter 17 #1

| 2. | One way that project management differs from management of more traditional activities is the limited life-time of projects. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 1 Stevenson - Chapter 17 #2

| 3. | Once a project is underway, project managers are only responsible for effectively managing time and costs. FALSE |
| --- | --- |

Difficulty: Easy Learning Objective: 1 Stevenson - Chapter 17 #3

| 4. | Projects typically go through a life cycle. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 1 Stevenson - Chapter 17 #4

| 5. | Some organizations use a matrix organization to integrate the activities of specialists within a functional framework. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 1 Stevenson - Chapter 17 #5

| 6. | A project manager usually staffs the human resources required for a project by hiring outside specialists that only work for the company for the duration of the project. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 1 Stevenson - Chapter 17 #6

| 7. | Project managers must often function in an environment that is beset with uncertainties. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 1 Stevenson - Chapter 17 #7

| 8. | The probability of occurrence of risk events is lower near the beginning of a project and higher near the end of the project. FALSE |
| --- | --- |

Difficulty: Easy Learning Objective: 2 Stevenson - Chapter 17 #8

| 9. | The costs associated with risk events tend to be lower near the beginning of a project, and higher near the end of the project. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 2 Stevenson - Chapter 17 #9

| 10. | The task of identifying risks should involve everyone associated with the project. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 2 Stevenson - Chapter 17 #10

| 11. | A list of risks and other key information collected as part of risk management planning is stored in a risk register. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 2 Stevenson - Chapter 17 #11

| 12. | Risks involved in a project can be transferred by outsourcing a particular component of the project and requiring performance bonds. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 2 Stevenson - Chapter 17 #12

| 13. | A hierarchical listing of what must be done during a project is called matrix. FALSE |
| --- | --- |

Difficulty: Easy Learning Objective: 2 Stevenson - Chapter 17 #13

| 14. | An advantage of Gantt charts in project management is that they reveal which activities can be delayed without delaying the overall project. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #14

| 15. | A Gantt chart reveals the sequence of activities in a project. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #15

| 16. | A Gantt chart can be a useful tool for simple projects. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #16

| 17. | Although PERT and CPM were originally developed for somewhat different types of projects, they are now nearly identical in terms of analysis and procedures. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #17

| 18. | PERT was originally developed for projects that had high levels of uncertainty. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #18

| 19. | The precedence network for a project describes sequential relationships among major activities in a project. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #19

| 20. | The path in a PERT/CPM precedence network with the fewest activities is referred to as the critical path. FALSE |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #20

| 21. | The path in a precedence network with the shortest duration is the critical path. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #21

| 22. | The sum of activity durations of the longest path in a network indicates expected project completion time, and the activities on it are called the critical activities. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #22

| 23. | The critical path has zero path slack time. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #23

| 24. | The earliest finish time for an activity is equal to the latest finish time minus the activity time. FALSE |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #24

| 25. | The latest starting time for an activity is equal to the latest finish time minus the activity time. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #25

| 26. | The earliest finish time for an activity is equal to the latest finish time minus the activity slack. TRUE |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #26

| 27. | Activity slack is the difference between the latest finish and earliest finish times. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 4 Stevenson - Chapter 17 #27

| 28. | Activities not on the critical path have a slack time equal to zero. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #28

| 29. | If two consecutive activities on the same path each have two days of activity slack, this means that each of them can be delayed by two days without delaying the project. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #29

| 30. | If two consecutive activities on the same path have shared slack, this means that each of them could use half of the slack without delaying completion of the project. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #30

| 31. | Deterministic networks use three duration estimates for each activity in order to best determine the activity's estimated duration. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #31

| 32. | A normal distribution is usually used to describe probabilistic duration estimates for activities in a project. FALSE |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #32

| 33. | A beta distribution is generally used to describe probabilistic project duration. FALSE |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #33

| 34. | The variance of project duration is equal to the sum of the variances of all the activities of the project. FALSE |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #34

| 35. | The standard deviation of the critical path is equal to the square root of the sum of the variances of all of the activities on the critical path. TRUE |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #35

| 36. | If the expected length of a path is more than 2.5 standard deviations less than a desired project completion time, the path would not be a factor in assessing the probability of finishing the project on time. FALSE |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #36

| 37. | In order to determine the probability of timely project completion, it is sometimes necessary to take into account paths other than the critical path. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #37

| 38. | The probability that the project will go beyond the desired time is equal to one minus the joint probability that all paths will be completed within the desired time. TRUE |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #38

| 39. | Simulation can be used for cases in which network activity durations are dependent. TRUE |
| --- | --- |

Difficulty: Easy Learning Objective: 5 Stevenson - Chapter 17 #39

| 40. | Project managers are sometimes able to reduce indirect project costs by increasing direct costs. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #40

| 41. | Only activities on the critical path are initial candidates for crashing. TRUE |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #41

| 42. | The optimum project length in crashing occurs where the cumulative cost of crashing equals savings in the indirect costs. TRUE |
| --- | --- |

Difficulty: Hard Learning Objective: 6 Stevenson - Chapter 17 #42

| 43. | Scope creep refers to the tendency for projects to take longer than planned. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 7 Stevenson - Chapter 17 #43

| 44. | The cost control technique of earned value analysis measures project progress by the budgeted cost of work scheduled. FALSE |
| --- | --- |

Difficulty: Medium Learning Objective: 7 Stevenson - Chapter 17 #44

| 45. | Which of the following would probably not involve the use of project management? A.; planning and constructing a new city hall. B.; developing an advertising campaign for a new product. C.; designing and constructing a subway system. D.; scheduling workers for a production plant. E.; preparing for the visit of a foreign dignitary. |
| --- | --- |

Difficulty: Easy Learning Objective: 1 Stevenson - Chapter 17 #45

| 46. | The life cycle of a project includes which of the following phases: I) initiation II) planning and scheduling III) growth and maturity IV) closeout A.; I and II. B.; II and III. C.; I, II and IV. D.; II, III and IV. E.; I, II, III and IV. |
| --- | --- |

Difficulty: Medium Learning Objective: 1 Stevenson - Chapter 17 #46

| 47. | Workers on a project are: A.; often on loan from their regular job. B.; often working only part-time on the project. C.; usually on the project for less than its full completion. D.; all of the choices. |
| --- | --- |

Difficulty: Medium Learning Objective: 1 Stevenson - Chapter 17 #47

| 48. | Once a project is underway, the project manager is responsible for effectively managing: I) the people II) costs III) time A.; I. B.; II. C.; III. D.; I and II. E.; I, II and III. |
| --- | --- |

Difficulty: Medium Learning Objective: 1 Stevenson - Chapter 17 #48

| 49. | Project planning involves all but which of the following? A.; Risk management planning. B.; Capacity expansion planning. C.; Quality planning. D.; Communication planning. E.; Purchase planning. |
| --- | --- |

Difficulty: Medium Learning Objective: 2 Stevenson - Chapter 17 #49

| 50. | Risk avoidance can be done by all but which of the following actions? A.; Extending the schedule. B.; Reducing project scope. C.; Creating contingency funds. D.; Clarifying requirements. E.; All of these are risk avoidance actions. |
| --- | --- |

Difficulty: Medium Learning Objective: 2 Stevenson - Chapter 17 #50

| 51. | Which of the following is not a form of risk reduction in project management? A.; backup systems. B.; outsourcing components of the project. C.; frequent monitoring of project activities. D.; expand the project scope to reduce external dependencies. E.; Improving communications. |
| --- | --- |

Difficulty: Medium Learning Objective: 2 Stevenson - Chapter 17 #51

| 52. | A hierarchical listing of what must be done in a project is called: A.; work breakdown structure (WBS). B.; program evaluation and review technique (PERT). C.; planning matrix. D.; crashing. E.; critical path method (CPM). |
| --- | --- |

Difficulty: Easy Learning Objective: 2 Stevenson - Chapter 17 #52

| 53. | The project management technique that is repeated until activities are decomposed into work packages that can be performed by a designated worker, team or subcontract is called: A.; work breakdown structure (WBS). B.; program evaluation and review technique (PERT). C.; planning matrix. D.; crashing. E.; none of the choices. |
| --- | --- |

Difficulty: Easy Learning Objective: 2 Stevenson - Chapter 17 #53

| 54. | Which of the following is part of project scheduling? A.; identify resource requirements for activities. B.; activity duration estimates. C.; project crashing. D.; identify sequential dependencies among activities. E.; all the choices. |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #54

| 55. | A popular tool for planning and scheduling simple projects is the: A.; activity-on-arrows network. B.; activity-on-nodes network. C.; Gantt chart. D.; critical path method. E.; program evaluation and review technique. |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #55

| 56. | The advantage(s) a Gantt chart has over other project scheduling techniques is (are): A.; its ability to reveal relationships among activities. B.; it can easily show networks.. C.; (a) and (b). D.; its simplicity. E.; all of the choices. |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #56

| 57. | The advantage(s) a precedence diagram has over a Gantt chart is (are): A.; its ability to reveal relationships among activities. B.; It can easily show networks.. C.; (a) and (b). D.; its simplicity. E.; all of the choices are correct.. |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #57

| 58. | Besides project activities, the primary information that all Gantt charts illustrate is: A.; project budget and when activities occur. B.; cost of activities and delays in the schedule. C.; planned duration of activities and when they occur in the schedule. D.; project budget and staffing levels. E.; critical path and project budget. |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #58

| 59. | Concerning PERT and CPM: A.; These are two different names for essentially the same technique.. B.; CPM tends to focus more on the critical path.. C.; PERT gives a clearer indication of activity slack, while CPM gives a better picture of path slack.. D.; Because of its recent discovery, much less is known about CPM than PERT.. E.; All of these are true.. |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #59

| 60. | Which of the following are advantages of CPM/PERT? I. It is visual. II. It is automatically updated. III. Activities that need to be watched closely can be identified. A.; I and II. B.; II and III. C.; III only. D.; I and III. E.; I, II, and III. |
| --- | --- |

Difficulty: Medium Learning Objective: 3 Stevenson - Chapter 17 #60

| 61. | In a precedence network the critical path is the sequence of activities which has: A.; the most activities. B.; the most nodes. C.; the most events. D.; the longest duration. E.; the greatest variance. |
| --- | --- |

Difficulty: Easy Learning Objective: 3 Stevenson - Chapter 17 #61

| 62. | Given the portion of the network shown above, what is the earliest finish time for activity D, if the earliest start time of B is 12, and the earliest start time of C is 13? A.; 19. B.; 20. C.; 21. D.; 22. E.; 23. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #62

| 63. | Activity 7 is directly preceded by two activities—activity 5 and activity 6. Activity 5 has an expected duration of five and an ES time of six. Activity 6 has an expected duration of seven and an ES time of seven. Activity 7 has an expected duration of 10. The ES for activity 7 is: A.; 11. B.; 14. C.; 21. D.; 24. E.; 25. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #63

| 64. | Which of the following is used to compute the earliest finish times once the earliest start times are calculated for activities on a precedence network? A.; expected project duration. B.; activity slack time. C.; which activities are on the critical path. D.; variance in project duration. E.; maximum project duration. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #64

| 65. | Given the portion of the network shown above, what is the latest start time of activity 7 if the latest finish of activity 8 is 26, and the latest finish of activity 9 is 23? A.; 18. B.; 17. C.; 13. D.; 12. E.; 10. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #65

| 66. | An activity, A, has two succeeding activities, B and C. Given the following information, determine the latest starting time for activity A. EF B = 15, EF C = 17, LF B = 24, LF C = 27; activity times are A = 4, B = 6, C = 8. A.; 14. B.; 15. C.; 16. D.; 17. E.; 18. |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #66

| 67. | Activity C has an early start time of 8, an early finish time of 12, a latest start time of 13, and a latest finish time of 17. Its slack is: A.; 0. B.; 1. C.; 4. D.; 5. E.; 9. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #67

| 68. | Given this information about activity B: ES = 10, EF = 15, LS = 16, and LF = 21, we can determine that the amount of slack associated with the activity is: A.; 0. B.; 1. C.; 5. D.; 6. E.; 11. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #68

| 69. | In precedence network analysis, knowing the slack time allows managers to: I) allocate scarce resources II) pay attention to activities that could delay the project III) delay critical activities A.; I. B.; II. C.; III. D.; I and II. E.; I, II and III. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #69

| 70. | In the probabilistic approach to precedence network analysis, the duration estimate annotated "tm" for any activity is the: A.; mean duration. B.; median duration. C.; most likely duration. D.; optimistic duration. E.; pessimistic duration. |
| --- | --- |

Difficulty: Easy Learning Objective: 5 Stevenson - Chapter 17 #70

| 71. | In the probabilistic approach to precedence network analysis, the duration estimate that is given the highest weighting in calculating the expected duration for an activity is: A.; duration of the immediately prior activity. B.; duration of the immediately following activity. C.; most likely duration. D.; optimistic duration. E.; pessimistic duration. |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #71

| 72. | When developing probabilistic estimates of project duration, it is necessary to know which of the following? A.; the mean and variance of every activity. B.; the mean and variance of activities on the critical path. C.; the standard deviation of activities on the critical path. D.; each activity's probability of completion. E.; the distribution of activity durations. |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #72

| 73. | A PERT/CPM activity has an optimistic duration estimate of three days, a most likely duration estimate of eight days, and a pessimistic duration estimate of 10 days. The expected duration of this activity is: A.; 7.0. B.; 7.5. C.; 8.0. D.; 8.5. E.; 10.0. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #73

| 74. | Activity 4 in a network diagram has an optimistic duration estimate of five days, a most likely duration estimate of seven days, and a pessimistic duration estimate of 10 days. Its expected duration is approximately: A.; 5. B.; 6. C.; 7. D.; 8. E.; 9. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #74

| 75. | There are four activities on the critical path, and they have standard deviations of 1, 2, 4, and 2 days. The standard deviation of the critical path is: A.; 3. B.; 5. C.; 9. D.; 16. E.; 25. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #75

| 76. | There are four activities on the critical path. Coincidentally, their standard deviations are all equal to 4. The standard deviation of the critical path is therefore equal to: A.; 2. B.; 4. C.; 8. D.; 16. E.; 64. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #76

| 77. | The project management strategy of injecting additional resources in order to reduce the length of the project is called: A.; expediting. B.; rushing. C.; panicking. D.; crashing. E.; none of the choices are correct.. |
| --- | --- |

Difficulty: Easy Learning Objective: 6 Stevenson - Chapter 17 #77

| 78. | In "crashing" a project, a manager will generally focus on activities which: A.; are not on the critical path. B.; are the least costly to crash. C.; are costly to crash and are on the critical path. D.; are on the critical path and are the least costly to crash. E.; none of the choices are correct.. |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #78

| 79. | At which point does crashing of a project cease? A.; when the project is completed. B.; when no additional crashing is possible. C.; when the cost to crash equals or exceeds the benefit of crashing. D.; all of the choices. E.; none of the choices. |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #79

| 80. | Uncontrolled growth in the number of activities that end up being included as part of a project is called: A.; the critical path. B.; project slack. C.; scope creep. D.; indirect costs. E.; time-cost-tradeoffs. |
| --- | --- |

Difficulty: Hard Learning Objective: 7 Stevenson - Chapter 17 #80

| 81. | Which of the following is not an advantage to using project management software? A.; It automatically generates and formats a variety of reports.. B.; It reduces project costs.. C.; It can enhance communication among team members.. D.; It can generate various charts.. E.; It provides a logical planning structure.. |
| --- | --- |

Difficulty: Hard Learning Objective: 8 Stevenson - Chapter 17 #81

|  | Given this network. |
| --- | --- |

Stevenson - Chapter 17

| 82. | The expected duration of this project is: A.; 12. B.; 17. C.; 20. D.; 36. E.; 77. |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #82

| 83. | The critical path for the network shown is: A.; a-c-g. B.; a-d-f-g. C.; a-d-h-i. D.; b-e-f-g. E.; b-e-h-i. |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #83

|  | Given this network. |
| --- | --- |

Stevenson - Chapter 17

| 84. | The expected duration of this project is: A.; 11. B.; 19. C.; 20. D.; 36. E.; 86. |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #84

| 85. | The critical path for the network shown is: A.; 1-2-6-7. B.; 1-2-4-7. C.; 1-4-7. D.; 1-3-4-7. E.; 1-3-5-7. |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #85

|  | The Project Manager is about to begin a project comprised of the following six activities: |
| --- | --- |

Stevenson - Chapter 17

| 86. | What is the estimated expected (mean) duration for activity E? A.; 91 days. B.; 99 days. C.; 100 days. D.; 101 days. E.; 115 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #86

| 87. | What is the estimated standard deviation of the duration for activity E? A.; 2 days. B.; 3 days. C.; 4 days. D.; 16 days. E.; 24 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #87

| 88. | What is the estimated expected (mean) duration for project completion? A.; 100 days. B.; 140 days. C.; 199 days. D.; 200 days. E.; 440 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #88

| 89. | What is the estimated slack time for activity A? A.; 0 days. B.; 20 days. C.; 40 days. D.; 60 days. E.; 100 days. |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #89

| 90. | What is the probability that this project will be completed within 205 days? A.; 0.6826. B.; 0.8413. C.; 0.9544. D.; 0.9772. E.; 0.9987. |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #90

|  | The owner of Ace Building Co. is about to begin work on a project comprised of the following four activities: |
| --- | --- |

Stevenson - Chapter 17

| 91. | What is the estimated expected (mean) duration for activity D? A.; 32 days. B.; 41 days. C.; 44 days. D.; 42 days. E.; 40 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #91

| 92. | What is the estimated standard deviation of the duration for activity D? A.; 0 days. B.; 2 days. C.; 3 days. D.; 4 days. E.; 12 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #92

| 93. | What is the estimated expected (mean) duration for project completion? A.; 41 days. B.; 70 days. C.; 100 days. D.; 120 days. E.; 221 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #93

| 94. | What is the estimated slack time for activity D? A.; 0 days. B.; 19 days. C.; 20 days. D.; 79 days. E.; 80 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #94

| 95. | What is the probability that this project will be completed within 130 days? A.; .8413. B.; .90. C.; .9544. D.; .9772. E.; .9987. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #95

|  | A project manager for Durable Construction Co. is about to build a house involving the following six activities: |
| --- | --- |

Stevenson - Chapter 17

| 96. | What is the estimated expected (mean) duration for activity E? A.; 35 days. B.; 36 days. C.; 39 days. D.; 40 days. E.; 45 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #96

| 97. | What is the estimated standard deviation of the duration for activity E? A.; 1 days. B.; 2 days. C.; 3 days. D.; 4 days. E.; 5 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #97

| 98. | What is the estimated expected (mean) duration for project completion? A.; 160 days. B.; 170 days. C.; 200 days. D.; 210 days. E.; 300 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #98

| 99. | What is the estimated slack time for activity D? A.; 0 days. B.; 30 days. C.; 40 days. D.; 50 days. E.; 100 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #99

| 100. | What is the probability that the critical path for this project will be completed within 210 days? A.; 0.5000. B.; 0.8413. C.; 0.9544. D.; 0.9772. E.; 0.9987. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #100

|  | A project superintendent is about to begin work on a freeway resurfacing project, which is comprised of the following five activities: |
| --- | --- |

Stevenson - Chapter 17

| 101. | What is the estimated expected (mean) duration for Activity E? A.; 31 weeks. B.; 38 weeks. C.; 39 weeks. D.; 40 weeks. E.; 43 weeks. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #101

| 102. | What is the estimated standard deviation of the duration for activity E? A.; 0 weeks. B.; 1 week. C.; 2 weeks. D.; 3 weeks. E.; 4 weeks. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #102

| 103. | What is the estimated expected (mean) duration for project completion? A.; 35 weeks. B.; 39 weeks. C.; 50 weeks. D.; 104 weeks. E.; 105 weeks. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #103

| 104. | What is the estimated slack time for Activity E? A.; 0 weeks. B.; 3 weeks. C.; 9 weeks. D.; 11 weeks. E.; 12 weeks. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #104

| 105. | What is the probability that the critical path for this project will be completed within 52 weeks? A.; 0.1554. B.; 0.3108. C.; 0.3466. D.; 0.6554. E.; 0.8277. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #105

|  | The manager of a National Forest is about to undertake a reforestation project in a burned out area. The project will involve the following six activities: |
| --- | --- |

Stevenson - Chapter 17

| 106. | What is the estimated expected (mean) duration for activity Y? A.; 30 days. B.; 29 days. C.; 38 days. D.; 26 days. E.; 35 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #106

| 107. | What is the estimated standard deviation of the duration for activity Z? A.; 3 days. B.; 2 days. C.; 4 days. D.; 8 days. E.; 5 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #107

| 108. | What is the estimated expected (mean) duration for project completion? A.; 135 days. B.; 145 days. C.; 170 days. D.; 180 days. E.; 255 days. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #108

| 109. | What is the estimated slack time for activity W? A.; 0 days. B.; 25 days. C.; 35 days. D.; 45 days. E.; 85 days. |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #109

| 110. | What is the probability that the critical path for this project will be completed within 200 days? A.; 0.8413. B.; 0.9544.. C.; 0.9772. D.; 0.9974. E.; 0.9987. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #110

| 111. | Assume that you are the manager of the project described above. What probability would you assign to a project duration of more than 8.5 weeks? |
| --- | --- |

Difficulty: Hard Learning Objective: 5 Stevenson - Chapter 17 #111

| 112. | Using the information given, do the following: (i) Draw the precedence network diagram. (ii) Identify the critical path. (iii) Determine expected project duration. (i) Refer to the diagram above. (ii) The critical path is b-e-f-g. (iii) Expected project duration is 19 weeks. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #112

| 113. | Given the network diagram above, determine each of the following: (i) the activities which are on the critical path (ii) the expected project duration (iii) the probability that the project will be completed in 29 weeks or less (Note: the numbers on each node refers to the expected duration and standard deviation in weeks for that activity. E.G., 8,2 indicates an expected duration of eight and a standard deviation of two weeks.) (i) The critical path is C-E-H. (ii) Expected project duration is 25 weeks. (iii) Except for the critical path, it appears that the project will easily finish on time due to their large z values. The probability of critical path completion by week 29 is .7881. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #113

| 114. | Determine the amount of slack in each of a project's activities (see the list below), and identify those which are on the critical path. |
| --- | --- |

Difficulty: Medium Learning Objective: 4 Stevenson - Chapter 17 #114

| 115. | Given the network diagram, determine the probability that the project will finish within 19 weeks of its start. Durations on the diagram are in weeks. |
| --- | --- |

Difficulty: Hard Learning Objective: 4 Stevenson - Chapter 17 #115

| 116. | A project consists of nine major activities, as shown. There are three separate paths in the network: a-c-f, b-d-g, and e-h-i. (i) What is expected project duration time? (ii) Determine the probability that the project will take more than 35 weeks to complete. (All durations are in weeks.) (i) 32 wk. (ii) P(Project<35) = (.9525) (.9082) (.8413) = .728. P(Project>35) = 1- .728 = .272. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #116

| 117. | Activity E has an optimistic duration of 9 days, a most likely duration of 12 days, and a pessimistic duration of 15 days. Estimate its expected duration and standard deviation. |
| --- | --- |

Difficulty: Easy Learning Objective: 5 Stevenson - Chapter 17 #117

| 118. | A project has the activities and activity durations (days) listed below. There are two paths: start-A-B-end and start-C-D-finish. Determine the probability that the project will require more than 15 days from start to finish. |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #118

| 119. | Activity D has an optimistic duration of 3 days, a pessimistic duration of 9 days, and a most likely duration of 4 days. Determine its expected duration and variance. te = (t0+4tm+tp)/6 = {3+4(4)+9}/6 = 4.67 var = (tp-t0)2/36 = (9-3)2/36 = 1 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #119

| 120. | What is the probability that this project will take more than 10 weeks to complete if the mean and standard deviations activity durations and the network diagram are as shown below: |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #120

Stevenson - Chapter 17

| 121. | What are the estimated expected (mean) durations (in weeks) for activities A-H? 15; 20; 10; 35; 25; 30; 20; 5 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #121

| 122. | What are the estimated standard deviations (in weeks) of the durations for activities A-H? 2; 1.67; 2; 4; 1.33; 3; 2; 1 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #122

| 123. | What is the estimated expected (mean) duration (in weeks) for project completion? 75 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #123

| 124. | What are the estimated slack times (in weeks) for activities A-H? 0; 5; 15; 0; 5; 15; 0; 0 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #124

| 125. | What is the critical path for this project network? Activities A-D-G-H |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #125

| 126. | What is the estimated standard deviation (in weeks) for the critical path completion time? 5 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #126

| 127. | What is the probability that the critical path for this project will be completed within 75 weeks? 80 weeks? 85 weeks? 90 weeks? .5; .8413; .9772; .9987 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #127

| 128. | Within what amount of time (in weeks) is there a 90% probability that the critical path for this project will be completed? 95%? 99%? 81.4; 83.25; 86.65 |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #128

Stevenson - Chapter 17

| 129. | What activities make up the critical path? Critical path: A-D-F-H |
| --- | --- |

Difficulty: Medium Learning Objective: 5 Stevenson - Chapter 17 #129

| 130. | In crashing this project, which activity is the first to be reduced? A costs $8,000, D costs $6,000, F costs $7,000, and H costs $12,000 Reduce activity D at $6,000. |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #130

| 131. | In crashing this project to 18 weeks, which activities (in order of selection) will be reduced? |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #131

| 132. | What is the total cost of reducing this project by two weeks? Total cost = $14,000 |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #132

| 133. | What is the total cost of reducing the project to 18 weeks? Total cost = $40,000 |
| --- | --- |

Difficulty: Medium Learning Objective: 6 Stevenson - Chapter 17 #133

| 134. | Indirect cost for a project is $2500 per day. Given the following information, determine an optimum crashing plan. What is the total cost for the plan? CRITICAL PATH = A-C-D-F-G Can crash 5 days at a cost of $6,900 |
| --- | --- |

Difficulty: Hard Learning Objective: 6 Stevenson - Chapter 17 #134

Chapter 17 Project Management Summary

| Category | # of Questions |
| --- | --- |
| Difficulty: Easy | 25 |
| Difficulty: Hard | 24 |
| Difficulty: Medium | 85 |
| Learning Objective: 1 | 11 |
| Learning Objective: 2 | 11 |
| Learning Objective: 3 | 18 |
| Learning Objective: 4 | 23 |
| Learning Objective: 5 | 56 |
| Learning Objective: 6 | 11 |
| Learning Objective: 7 | 3 |
| Learning Objective: 8 | 1 |
| Stevenson - Chapter 17 | 143 |