Chapter 1

- Project is a unique venture with a beginning and end, conducted by people to meet goals within parameters or cost, schedule and quality.

- Projects are goal oriented, interrelated activities, finite duration, to a degree, unique

- Project:

- Have a specific objective

- Have defined start and end dates

- Have funding limits

- Consume human and nonhuman resources

- Multifunctional

- Complex, one time processes

- Limited by budget, schedule and resources

- Projects are developed to resolve a clear goal or set of goals

- Projects are customer focused

- Projects are ad hoc endeavors with a clear life cycle

- Projects are building blocks in the design and execution of organizational strategies

- Are responsible for the newest and most improved products, services and organizational processes

- Provide a philosophy and strategy for the management of change

- Management entails crossing functional and organizational boundaries

- Traditional management functions of planning, organizing, motivation, directing and control apply to project management

- Principal outcomes of a project are the satisfaction of customer requirements within the constraints of technical, cost, and schedule objectives

- Are terminated upon successful completion of performance objectives

- Why are projects important?

- Shortened product life cycles

- Narrow product launch windows

- Increasingly complex and technical products

- Emergence of global markets

- Economic period marked by low inflation

- Project life cycle is the stages of a project’s development:

- Conceptualization: initial goal, scope, resources, stakeholders

- Planning: work packages, steps of process

- Execution: actual work is performed, developed, product created and fabricated

- Termination: completed project is transferred to client, project closed out

- 5 components of a project:

- Client interest

- Project stake

- Resources

- Creativity: degree of innovation

- Uncertainty: degree of risk

- Project success: time, budget, performance, client acceptance

- 4 relevant dimensions of success: project efficiency, impact on customer, business success, preparing for the future

- Project management maturity models are used to allow organizations to benchmark best practices of successful firms

- Benchmarking is to systematically manage the process improvements of project delivery over time

- Project manager is faced with responsibilities:

- Selecting a team, developing project objectives and a plan for execution, performing risk management activities, cost estimating and budgeting, scheduling, managing resources

Chapter 5

- Project delivery system: contracting method or contract strategy or procurement strategy = framework for the relationships b/w owner and other project participants

- Exposes the parties involved to certain risk and uncertainty

- Increase in uncertainty = increase in costs and disputes

- Goals: Minimize uncertainty by allocating project risk

- 4 general types:

- traditional project or design big build:

owner enters in 2 contracts: 1 with single designer and 1 with single general contractor

- turnkey project (design manager and design build):

for large industrial projects that require specialized knowledge and skills not widely  available = oil, power plants, etc

- owner building project:

owner is responsible for the design and construction and fabrication (municipalities, ministries)

- professional construction management (professional construction management construction manager and construction management at risk):

used for very large projects (design all the buildings for a street)

Chapter 6

- Key scheduling terminology:

- How activity networks are constructed

- Task durations are estimated

- Critical path and activity float are calculated

- Lag relationships are built into relationships

- Create activity networks: use network logic in order to identify activities that are considered predecessors (earlier in the network) and successors (after/later the predecessor activities)

- Activity on Node (AON) techniques: applies the logic of assigning all tasks as specific nodes in the network and linking them with arrows to identify the predecessor-successor relationships

- Activity duration estimation: identify the various tasks in a project and apply a method for estimating the duration of each of these activities. Methods:

- Noncomputational techniques

- Deriving duration estimates through computational or mathematical analysis

- Program Evaluation and Review Technique (PERT) which uses probabilities to estimate a task’s duration = (optimistic + 4x most likely + pessimistic) /6

- Steps to reduce critical path:

- Eliminate tasks on critical path

- Replan serial paths to be in parallel

- Overlap sequential tasks

- Shorten the duration of critical path tasks

- Shorten early tasks

- Shorten longest tasks

- Shorten easiest tasks

- Shorten tasks that cost the least to speed up

- P 103

Forward pass: at a merging point, the largest preceding EF comes the ES for that node

EF = ES + Duration

EF becomes the ES of next node

Backward pass: at a split point, the smallest succeeding LS becomes the LF for that node

LS = LF – Duration

LS becomes the LF of next node

LOOK AT ASSIGNMENT 2

Chapter 7

- Types of common project costs: cost estimation and budgeting process

- Expenses in projects:

- Cost of labor

- Cost of materials

- Subcontractors: use of consultants

- Cost of equipment and facilities

- Travel

- Types of costs:

- Direct vs indirect: direct is directly assigned to project = shipping costs, commissions, / indirect is other expenses like health benefits, contribution

- Recurring vs nonrecurring: recurring are ongoing expenses = labor and material/ variable increases in proportion to the degree they are used

- Normal vs expedited: expedited = crashing costs that are more expensive because of speed of completion of task

- Cost estimation:

- Preliminary estimates: ballpark estimates = accurate to only +- 30%

- As you get closer to design phase: definitive estimates = +- 5%

- Use of parametric techniques which compare current project activities to the cost of past, similar activities and then assign a multiplier that considers inflation

- Parametric cost estimation:

- Allows managers to develop detailed estimated of current project costs by taking older work and inserting a multiplier to account for impact of inflation, labor, materials, direct costs

- Allows managers to begin formulating cost estimates from a position of past record

- VERY IMPORTANT ELEMENT: effect of learning rates on individual’s ability to perform a task = learning curves or computation of the nth iteration

- Why project cost estimation is done poorly:

- Low initial estimates: poor knowledge of product’s scope

- Unexpected technical difficulties

- Lack of definition: poor specified projects = poor budgeted and controlled projects

- Specification changes: cost overruns

- External factors: inflation, economic, political interference

- Project budgeting:

- Top down and bottom up procedures

- 1: identify the activities that consume resources and assign costs to them

- 2: determine the cost drivers associated with the activities (human resources and materials)

- 3: compute a cost rate per cost driver

- This allows for creation of project budgets with specific budget lines for each task

- Time phased budgeting:

- Allows the team to link time and cost into a unified baseline that can be set to serve as the project plan

- As the project moves forward, project cost control is created

- Contingency funds: money set aside from the initial cost estimation for unexpected events into an account called the project contingency fund

- It is not assigned to any activity

- Only used as emergency fund to handle problems

Chapter 8

- Earned Value Management (EVM): variance analysis = project control technique used in industries such as construction industry

- Integrates project’s scope, cost, performance and progress

- One of the best project control techniques for early detection of performance

- Cost schedule plan: plot of cost (y axis) vs time (x axis)

- P157 and p158

- ASSIGNMENT 4

- Actual quantity of work completed / total quantity of work = % completed

Earned value (EV) = % complete x total budgeted cost

- Cost Variance  = Earned Value – Actual Value

CV  = EV – AC

- Scheduled Variance = Earned Value – Planned Value

SV = EV – PV

- Cost Performance Index = Earned Value/ Actual Value

CPI = EV / AC

- Scheduled Performance Index = Earned Value/ Planned Value

SPI = EV / PV

- Estimated Remaining Cost to Completion = (Total PV – Earned Value) / CPI

ETC = (BAC - EV) / CPI ---- TYPPICAL FOR FUTURE VARIANCES

ETC = BAC – EV --- ATYPICAL FOR FUTURE VARIANCES

- Project total cost At Completion = ETC + AC

EAC = ETC + AC

Chapter 9

- Interest: the difference between the amount of money lent and the amount of money later repaid

- Future amount = Principal amount (1+interest rate)

F = P+ Pi = P(1+i)

- Simple interest:

F = P(1 + i)N where N= number of interest periods

Or

I = PiN

- Compounding:

Total interest on N period=

I=  P(1 + i)N – P