TRANSPORTATION How many tons of wheat to transport from each grain elevator to each mill each month to minimize total cost of transpo (select shipping routes & units to be shipped)

Decision Var: Xij: number of units shipped from origin I to destination J (where i=1,2,3) to mill j (where j=A,B,C)                                                                         Object: min Z = $ 6x1A + 8x1B + 10x1c + 7x2A+ 11x2B + 11x2C + 4x3A + 5x3B + 12x3C

Constraints: deal with capacities at each origin, deal with req at each destination (demands), six constraints: one for each elevator supply also for each mill demand

x1A + x1B + x1C = 150		x1A + x2A+ x3A = 200

x2A + x2B + x2C = 175		x1B+ x2B + x3B = 100

x3A + x3B + x3C = 275		x1C + x2C + x3C = 300		xij ≥ 0

When Total Supply>Total Demand: appear as slack		Total Supply<Total Demand: some destination unsatisfied demand

Route capacities: Xij <= Lij or minimum: Xij >= Mij		Unacceptable routes: make Xij = 0

| ES | EF | LS | LF | Slack |
| --- | --- | --- | --- | --- |
| Max EF of immediate predecessors | ES+duration | LF-duration | Min LS of immediate following activities | ES-LF or LF-EF |

PROJECT SCHEDULING Earliest Start, Earliest Finish, Latest Start, Latest Finish

| Activity | A | B | C | D | E | F | G | H | I |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Immediate Predecessors | -- | A | A | B | B | C,E | D,E | F,G | H |
| Duration | 5 | 18 | 13 | 3 | 10 | 11 | 4 | 9 | 2 |

a) max # working days needed to complete all activities if no delays? 55 days

b) crit activities? the ones with no slack CPM

PERT

Most likely time =(m) 	optimistic time =(a)	       pessimistic time= (b)

Expect Activity Time (t)	= (a+4m+b)/6

Variance  			=  [ (b - a) / 6 ] 2

Standard deviation  =  Variance =  (b - a) / 6

Expected Project Completion Time (tp) = Sum of the expected (mean) time of all the activities on the critical path.

Project variance 		= Σ(variances of activities on critical path)

Project standard deviation (σp) 	=  (Project variance)

Z = (due date – expected completion time) / σp

Due Date  =  Expected completion time + Z x σP

DECISION ANALYSIS

1. Clearly define the problem at hand

2. List all the possible alternatives (decisions to be made)

3. Identify the possible outcomes (state of nature) of each alternative

4. List the payoff or the profit of each combination of alternatives and outcomes

5. Select 1 of the mathematical decision theory models(ex:Decision Making under Risk)

6. Apply the model and make your decision

If Under Certainty

Maximax: choose max value of all the max pay-offs - optimistic

Maximin: choose max of all the min pay-offs - conesrvative

Equally Likely Criterion: calc row average -> choose max

Minimax: take minimum of the calculated max regret

Under Risk (probabilities assigned to states of nature)

Ex: based on economic forecast, able to estimate 60% good economy, 40% poor

EMV(Expected Monetary Value)=outcome 1st nature*its prob + outcome 2nd * its prob

Best decision is one with the highest EMV(if in terms of cost, choose lowest)

EOL(Expected Opp Loss) = regret 1st nature *its prob + regret 2nd nature *its prob…

Choose the minimum of all these values

EVPI(Expected val of Perfect Info)= (best outcome for first state of nature)x(its prob.) + (best outcome for second state of nature)x(its prob.)

EV of PI = EV with PI – EMV

Shows max amount that would be paid to gain info that would result in decision better than one made without perfect info

EVSI = expected value with information – expected value without information

Efficiency,η = EVSI / EVPI

A high efficiency rating indicates that info is very good, or close to being perfect info

A low ‘η’ rating indicates that the additional information is not very good.

If relatively high; it is doubtful that the investor would seek additional information from an alternative source.

GOAL PROGRAMMING Decide what to produce over the next quarter. A product cannot be produced unless the associated set-up cost is paid. If the set-up cost is paid, the amount of a product which is produced is limited by the associated capacity. Product B is always packaged in quantities of 100(if produced either: 100, 200 or 300 units). However, the other products have no such packaging requirements. If all 4 products produced, an extra charge of $1000 is incurred for training

There are three goals (equally weighted):

1) total profit should be at least $8000  2) total set-up cost should be at most 950

3) exactly three products should be produced

The objective as usual is to minimize the sum of the appropriate deviations (i.e., the deviations which are deemed to be undesirable). FORMULATE the above problem.

* Let A, B, C and D denote the number of units of each of the products produced

* Let yA, yB, yC and yD = 1 if the corresponding product is produced, 0 otherwise

* Let zi = 1 if 100i units of C are produced, 0 otherwise (i=1,2,3)

* Let w = 1 if all four products are produced, 0 otherwise  Let di+ and di– denote the amounts by which the ith goal is over(under)-achieved

* Minimize d1+ + d2– + d3+ + d3–

* A≤400yA * B≤300yB * C≤500yC  		* D≤250yD

** B = 100z1 + 200z2 + 300z3 			** z1 + z2 + z3 ≤ 1

** yA + yB + yC + yD ≤ 3+w

*  10A + 8B + 6C + 7D – 1200yA – 600yB – 700yC -1000w = 8000 + d1+ – d1–

*  1200yA + 600yB + 700yC = 950 + d2+ – d2–

*  yA + yB + yC + yD = 3 + d3+ – d3–

*  A, B, C and D either ≥ 0 or integer deviation variables ≥ 0 	* yi, zi, w binary

d1-: underachievement of the profit target

d1+ : overachievement of the profit target

As much profit above 3000$ as possible d-	Fully utilize available wiring d+

Avoid overtime in assembly d+	Meet contract to produce at least seven ceiling d+

eg: $600X1 + $700X2 + d1- - d1+ = $3,000 (profit goal – always minimize d’s)

all di variables >= 0 in 4th step

If equally important goals

Min. total deviation = d1- + d2- + d3+ + d4-

$600X1 + $700X2 + d1- - d1+ = $3000 (profit constraint)

2X1 + 3X2 + d2- - d2+  =12 	(wiring hours)

If priority goals

Min. total deviation = P1d1- + P2d2- + P3d3+ + P4d4- (as priorities are listed)

If weighted goals

Min. total deviation = 40d1- + 30d2- + 20d3+ + 10d4- (as weights are listed)

If you can go above the goal then MinZ = d-, below then MinZ = d+

INTEGER PROGRAMMING Want to determine locations for cab waiting points.

| Location | Can Serve Areas | Cost/ Day |
| --- | --- | --- |
| 1 | A, E | $400 |
| 2 | A, C, D | $500 |
| 3 | B, C, E | $450 |
| 4 | B, D | $440 |
| 5 | D, E | $430 |

Wants to be sure all areas can be served and wants done for as little cost as possible. Determine choice of locations to accomplish this goal.

Xi = 1 if location 1 used, 0 if otherwise (i= 1 to 5)

Min Z = 400x1 + 400x2 + 450x3 + 440x4 + 430x5

Area A x1 + x2 >= 1		Area D x2 + x4 + x5 >= 1

Area B x3 + x4 >= 1		Area E x1 + x3 + x5 >= 1

Area C x2 + x3 >= 1		Xi E [0,1]

No more than 2 products can be produced

Yi = 1 if prod 1 produced 	y1+y2+y3+y4 <=2

If prod 3 or 4 produced then prod 1 or 2 must be produced

Y3 <= y1 + y2	y4 <= y1+y2

INTEGER PROGRAMMING Product can be made on only 1 of 2 machines: x1 or x2. Machines have different process req, profit & cost structures. Differences:

| Machine | Profit/Unit $ | Setup Cost | Raw Mat #1 /unit | Raw Mat #2/unit |
| --- | --- | --- | --- | --- |
| X1 | $50 | $250 | 2 lbs | 4 quarts |
| X2 | $40 | $210 | 3 lbs | 2 quarts |

Determine whether all output should be produced on one of machines or split between two machines. Maximize contribution to profit. 30 lbs of raw mat #1 and 36 quarts of raw mat #2 available for the production run.

x1 = # units to produce machine 1	x2 = # units produce machine 2

y1 = 1 if machine 1 used, 0 otherwise	y2 = 1 if machine 2 used, 0 otherwise

max Z= 50x1 + 40x2 – 250y1 – 210y2		where M is a very large #

2x1+3x2 <= 30	4x1+2x2 <= 36	x1 <= My1	x2 <= My2

x1, x2 integers >= 0	y1, y2 E [0,1]	x1 – My1 <= 0	x2 – My2 <= 0