EISEL QUESTIONS: 1) PROJECT INITIATION

Which of the following is/are criteria for project selection?

Is there a market offering for the project results

How risky is the project

Is the project synergistic with other important projects

All of the above   (1 points)

Which of the following is a valid weakness to the Gantt Chart?

What appears on the chart may require intimate knowledge of the project's technologies   (1 points)

Requires training to analyze

Difficult to read

Requires a lot of technical knowledge

You are the project manager of the Good Will project. The WBS has been created, activities have been defined, and resources have been estimated. It's time to estimate the duration for each activity. Which of the following should perform the activity duration estimate?

The project manager

The individual or the team that will do the work   (1 points)

The customer

The senior management

The project management team

New car models (example: Toyota Corolla 2014) have major changes in a number of areas which include manufacturing and product changes when they are released. This is an example of which project category?

Breakthrough projects

Platform projects   (1 points)

Derivative projects

R&D projects

In a Work Breakdown Structure, usually higher level tasks take the most amount of time compared to the lower levels in a project.

True

False   (0.5 points)

Which of the following is typically used as the best estimate of task duration?

expected time   (1 points)

pessimistic time

optimistic time

most likely time

none of the above

A Project charter affirms that all major parties of interest are in agreement on

schedules

cost

deliverables

all of the above   (1 points)

none of the above

Which of the following are projects?

the design and development of a new product   (1 points)

gathering and entering employment data for a Bureau of Labor Statistics quarterly report

producing a car on an automobile assembly line

a and b above.

a, b, and c above

Which of the following is not a characteristic of a project?

They are unique

They are routine   (1 points)

They have specific due date

They have a specific deliverable

They have a purpose

The type of work activity in project management is _______, compared to that of general management, which is ________.

Critical, Important

Unique, Routine   (1 points)

Informal, Well Defined

Important, Less Important

Which of the following best defines a project?

A set of schedule activities performed by a team that has a project manager

A set of sequential activities performed by using project management processes

A temporary endeavor undertaken to create a unique product, service, or result   (1 points)

An ongoing operation being performed to meet customer requirements

Which of the following is not a tool used to aid the PM in project control?

variance analysis

trend projections

earned value analysis

control charts

discounted cash flow analysis   (1 points)

Which of the following is NOT an element of the Gantt chart?

actual progress

variance of the critical path   (1 points)

the current date

scheduled milestones

all of the above are elements

You are starting a project in your company and are identifying the stakeholders. The CEO of your company is not directly involved in the project. Which of the following is not a key stakeholder in this project?

Investor   (1 points)

Project sponsor

PMO

Project manager

CEO of your company

Which of the following is not an element of a Project Charter?

Overview

Organization ethics   (1 points)

Evaluation methods

Schedules

Which of the following is a true statement about the WBS?

It is a deliverable-oriented hierarchical decomposition of the project work to be performed by the project team.   (1 points)

It's a hierarchically organized set of resources needed by the project.

It's a hierarchically organized set of risks identified for the project.

It represents the reporting hierarchy in the performing organization.

The __________________ constitutes a “closed-loop” process that continues until the project is completed.

Management cycle

Plan-monitor-control cycle   (1 points)

Time-cost-scope cycle

Progressive plan cycle

Milestones cannot be identified on a Gantt Chart.

True

False   (0.5 points)

A PERT project has 45 activities, 19 of which are on the critical path. The estimated time for the critical path is 120 days. The sum of all activity variances is 64, while the sum of variances along the critical path is 36. The probability that the project can be completed between days 108 and 120 is

-2.00

0.0227

0.1058

0.4773   (1 points)

0.9773

Which of the following is an important project manager role?

technical expert

supervisor

project champion

micromanager

communicator   (1 points)

Which of the following terms is most closely associated with a task required by the project?

activity   (1 points)

event

milestone

network

path

Starting the building phase before the design and planning phases is called…

operations overlapping

concurrent engineering

fast-tracking   (1 points)

concurrent construction

construction overlapping

A start-to-finish linkage is the most common way of linking to successive task.

True

False   (0.5 points)

Which of the following is a valid weakness to the Gantt Chart?

What appears on the chart may require intimate knowledge of the project's technologies   (1 points)

Requires training to analyze

Difficult to read

Requires a lot of technical knowledge

Which of the following is not a tool used in the scope definition process?

Expert judgment

Product analysis

Stakeholder analysis

Project charter   (0.5 points)

Which of the following is not an effective team member's characteristics (excluding the Project Manager)?

Technically competent

High-self esteem

Motivational   (1 points)

Problem orientation

All of the above

What is the primary purpose of creating a work breakdown structure?

to draw the project plan as a chart or tree

to make sure important tasks are identified   (1 points)

so that all team members can see what others are working on

to assign budget numbers to tasks

to make sure team members can communicate effectively

Which of the following best defines a project?

A set of schedule activities performed by a team that has a project manager

A set of sequential activities performed by using project management processes

A temporary endeavor undertaken to create a unique product, service, or result   (1 points)

An ongoing operation being performed to meet customer requirements

Which of the following terms is most closely associated with a task required by the project?

activity   (1 points)

event

milestone

network

path

Which of the following is a Project Manager's responsibility in a project?

Acquisition of personnel and resources

Dealing with obstacles that arise during the course of the project

Exercising the leadership needed to bring the project to success

All of the above   (1 points)

None of the above

Fairness: 3 / 5

Which of the following is a Project Manager's responsibility in a project?

Acquisition of personnel and resources

Dealing with obstacles that arise during the course of the project

Exercising the leadership needed to bring the project to success

All of the above   (1 points)

None of the above

Which of the following is the result of a project launch meeting?

The project's scope is understood and temporarily fixed   (1 points)

Any potential benefits to the organization outside of the scope of the project are ignored

The various team members understand their responsibilities

both a) and b)

both b) and c)

Which of the following does not affect the duration of a schedule activity?

Resources assigned to the activity

Availability of the assigned resources

Whether the activity is on a critical path   (1 points)

Experience of the human resource assigned

Top of Form

Which of the following is typically used as the best estimate of task duration?

expected time   (1 points)

pessimistic time

optimistic time

most likely time

none of the above

A Project charter affirms that all major parties of interest are in agreement on

schedules

cost

deliverables

all of the above   (1 points)

none of the above

The __________________ constitutes a “closed-loop” process that continues until the project is completed.

Management cycle

Plan-monitor-control cycle   (1 points)

Time-cost-scope cycle

Progressive plan cycle

The three primary goals of any project are:

profit, schedule, quality

schedule, budget, quality

performance, budget, schedule   (1 points)

performance, quality, schedule

budget, quality, profit

Which of the following is not true concerning the difference between the project manager (PM) and the traditional  manager (TM)?

the PM is a facilitator the TM is a technical supervisor

the PM is a generalist the TM is a specialist

the PM must be able to integrate tasks; the TM must be able to analyze tasks

the PM uses an analytical approach the TM uses a systems approach   (1 points)

all of the above are true

According to research, which of the following is not an important dimension of project success?

project efficiency

project team cohesiveness   (1 points)

customer impact/satisfaction

business/direct success

future potential

Which of the following are projects?

the design and development of a new product   (1 points)

gathering and entering employment data for a Bureau of Labor Statistics quarterly report

producing a car on an automobile assembly line

a and b above.

a, b, and c above

A matrix project that closely resembles the pure project is referred to as

a weak matrix

a strong matrix   (1 points)

a functional matrix

a balanced matrix

an unbalanced matrix

Which of the following should always be included in a project charter? (Choose one.)

Business case for the project   (1 points)

Statement of work

Project scope statement

Project management plan

Which of the following is the result of a project launch meeting?

The project's scope is understood and temporarily fixed   (1 points)

Any potential benefits to the organization outside of the scope of the project are ignored

The various team members understand their responsibilities

both a) and b)

both b) and c)

The first task of a newly appointed project manager is

to negotiate the project's budget

to negotiate with functional managers for key resources

to develop a work breakdown structure for the project

to review the project objectives with senior management   (1 points)

to develop a linear responsibility chart for the project

Which of the following types of organizations would likely not have a program manager?

functional project organization   (1 points)

pure project organization

strong matrix project organization

weak matrix organization

All of the above would likely have program managers

What is it a milestone?

a significant event in the project   (1 points)

a mark on a chart that depicts project progress

an activity on the critical path

an activity with an uncertain completion time

all of the above

Which of the following is not an element of a Project Charter?

Overview

Organization ethics   (1 points)

Evaluation methods

Schedules

Top of Form

Which of the following are the five process groups in project management? (Choose one answer.)

Initiating, planning, executing, monitoring, and controlling

Initiating, planning, executing, monitoring, and closing   (1 points)

Initiating, scoping, executing, monitoring, and closing

Initiating, planning, executing, testing, and closing

In a WBS, the Project Manager should be planning at what level?

Level 1   (1 points)

Level 2

Level 3,4 and 5

All of the above

Starting the building phase before the design and planning phases is called…

operations overlapping

concurrent engineering

fast-tracking   (1 points)

concurrent construction

construction overlapping

Which of the following is a valid weakness to the Gantt Chart?

What appears on the chart may require intimate knowledge of the project's technologies   (1 points)

Requires training to analyze

Difficult to read

Requires a lot of technical knowledge

According to research, which of the following is not an important dimension of project success?

project efficiency

project team cohesiveness   (1 points)

customer impact/satisfaction

business/direct success

future potential

Which of the following is/are criteria for project selection?

Is there a market offering for the project results

How risky is the project

Is the project synergistic with other important projects

All of the above   (1 points)

The __________________ constitutes a “closed-loop” process that continues until the project is completed.

Management cycle

Plan-monitor-control cycle   (1 points)

Time-cost-scope cycle

Progressive plan cycle

In a Work Breakdown Structure, usually higher level tasks take the most amount of time compared to the lower levels in a project.

True

False   (0.5 points)

Which of the following is not a project selection method?

Expert judgment

Scoring models

Benefit/cost ratio

Cash flow

Cost variance   (1 points)

The PM’s job includes all of the following except?

Convener and chair of meetings

Facilitator

Communicator

Supervisor   (1 points)

Virtual project manager

In a WBS, the Project Manager should be planning at what level?

Level 1   (1 points)

Level 2

Level 3,4 and 5

All of the above

A start-to-finish linkage is the most common way of linking to successive task.

True

False   (0.5 points)

Who is the best suited among the project stakeholders to plan Level 1 activities in a Work Breakdown Structure?

The Boss (CEO, CIO, etc.)

The entire project team

The Project Manager   (1 points)

The team specialists

Which of the following criteria can be included in scoring models for selecting projects?

potential profitability of the project

potential impact on the firm's competitive position

the organization's ability to market the output of a project

All of the above can be included   (1 points)

only a and b above

The type of work activity in project management is _______, compared to that of general management, which is ________.

Critical, Important

Unique, Routine   (1 points)

Informal, Well Defined

Important, Less Important

The project team members should be all of the following except:

politically sensitive

technically competent

goal oriented

problem oriented

focused on activities   (1 points)

Which of the following does not affect the duration of a schedule activity?

Resources assigned to the activity

Availability of the assigned resources

Whether the activity is on a critical path   (1 points)

Experience of the human resource assigned

Milestones cannot be identified on a Gantt Chart.

True

False   (0.5 points)

The first task of a newly appointed project manager is

to negotiate the project's budget

to negotiate with functional managers for key resources

to develop a work breakdown structure for the project

to review the project objectives with senior management   (1 points)

to develop a linear responsibility chart for the project

Which of the following terms is most closely associated with a task required by the project?

activity   (1 points)

event

milestone

network

path

During project formation stage, the major sources of conflict are all of the following except:

Priorities

Procedures

Technical   (1 points)

Schedules

Which of the following is NOT one of the four important dimensions of project success?

Efficiency

Future potential

Business/direct success

Customer impact/satisfaction

All of the above are part of the four dimensions.   (1 points)

Which of the following statements is not true about the project charter?

It determines the scope of the project.   (1 points)

It names the project manager for the project.

It authorizes the project manager to use organizational resources to perform project activities.

It provides a high-level product description.

Which of the following is NOT one of the four important dimensions of project success?

Efficiency

Future potential

Business/direct success

Customer impact/satisfaction

All of the above are part of the four dimensions.   (1 points)

Which of the following is an output of the scope definition process?

Project charter

Project scope statement   (1 points)      right ans

Preliminary project scope statement

Project schedule

A project being analyzed by PERT has 38 activities, 16 of which are on the critical path. If the estimated time along the critical path is 90 days with a project variance of 25, the probability that the project will be completed in 88 days or less is

0.0228

0.3446   (1 points)

0.6554

0.9772

18

Which of the following statements regarding critical paths is true?

The shortest of all paths through the network is the critical path.

Some activities on the critical path may have slack.

Every network has only one critical path.

On a specific project, there can be multiple critical paths, all with exactly the same duration.   (1 points)

The duration of the critical path is the average duration of all paths in the project network.

According to research, which of the following is not an important dimension of project success?

project efficiency

project team cohesiveness   (1 points)

customer impact/satisfaction

business/direct success

future potential

The three primary goals of any project are:

profit, schedule, quality

schedule, budget, quality

performance, budget, schedule   (1 points)

performance, quality, schedule

budget, quality, profit

EISEL QUESTIONS: 2) PLANNING

The __________________ constitutes a “closed-loop” process that continues until the project is completed.

Management cycle

Plan-monitor-control cycle   (1 points)

Time-cost-scope cycle

Progressive plan cycle

Which tool do PMs use to measure the volume of raw material being used, the cost of contract labour and the hours of computer time?

Cost chart

Benchmarking

Control chart   (1 points)

Critical ratio

Which of the following does not affect the duration of a schedule activity?

Resources assigned to the activity

Availability of the assigned resources

Whether the activity is on a critical path   (1 points)

Experience of the human resource assigned

The PM’s job includes all of the following except?

Convener and chair of meetings

Facilitator

Communicator

Supervisor   (1 points)

Virtual project manager

EISEL QUESTIONS: 3) EXECUTION

When looking at the variances on an earned value chart, a positive variance is ___ and a negative variance is ___.

Bad; Good

Good; Good

Good; Bad   (1 points)

Bad; Bad

The critical path for the network activities shown below is __________ with duration __________.

| Activity | Duration | Immediate Predecessors |
| --- | --- | --- |
| A | 2 | -- |
| B | 4 | -- |
| C | 6 | A,B |
| D | 1 | A,B |
| E | 2 | B,C,D |

A-D-E; 5

B-E; 6

B-D-E; 7

A-C-E; 10

B-C-E; 12   (1 points)

The critical path for the network activities shown below is __________ with duration __________.

| Activity | Duration | Immediate Predecessors |
| --- | --- | --- |
| A | 10 | --- |
| B | 8 | --- |
| C | 2 | A |
| D | 4 | A |
| E | 5 | B,C, D |

A-C; 12

A-D-E; 19   (1 points)

B-E; 13

A-B-C-D-E; 29

none of the above

To crash a project, which of the following principles apply? 1) Focus on the critical path(s) when trying to shorten the duration of a project, 2) Select the least expensive way to do it 3) Crash non-critical activities

All three are correct

Only 1 and 3 are correct

Only 1 and 2 are correct   (1 points)

Only 1 is correct

Which of the following linkages is used to start two or more activities at the same time?

finish-to-start

start-to-start   (1 points)

finish-to-finish

start-to-finish

They can all be used to start two or more activities at the same time.

Which of the following is not a trend in project management?

achieving strategic goals

improving project effectiveness

quasi projects

reductive projects   (1 points)

achieving routine goals

Calculation of a number called the ________ can reveal if there is systematic bias in cost and other estimates.

Difference

MAR

Tracking Signal   (1 points)

Estimate

In earned value analysis…

it is desirable to have negative variances for both schedule and spending.

it is desirable to have positive variances for both schedule and spending.   (1 points)

the schedule variance should be positive and the spending variance negative.

the schedule variance should be negative and the spending variance positive.

ideally both variances would equal zero.

Which of the following is not a trend in project management?

achieving strategic goals

improving project effectiveness

quasi projects

reductive projects   (1 points)

achieving routine goals

c (c) demonstrates:

A Negative schedule variance, positive spending variance

A Negative schedule variance, negative spending variance

A positive schedule variance, negative spending variance   (1 points)

All of the above

Which of the following statements regarding CPM is true?

The critical path is the shortest of all paths through the network.

The critical path is that set of activities that has positive slack.

Some networks have no critical path.

All activities on the critical path have their LS equal to the maximum EF of all immediate predecessors.   (1 points)

All of the above are false.

Which of the following is typically used as the best estimate of task duration?

expected time   (1 points)

pessimistic time

optimistic time

most likely time

none of the above

Which of the following is the correct formula to calculate the activity slope?

(crash cost - crash time)/(normal cost – normal time)

(crash cost – normal cost)/(crash time – normal time)   (1 points)

(normal cost – crash time)/(normal time – crash cost)

(normal cost – crash cost)/normal time – crash time)

An identifiable state resulting from the completion of one or more activities is called?

an event   (1 points)

an activity

a milestone

a path

the critical path

Top of Form

Activity D on a CPM network has predecessors B and C, and has successor F. D has duration 6. B's earliest finish is 18, while C's is 20. F's late start is 26. Which of the following is definitely true?

B is a critical activity.

C is completed before B.

D has no slack but is not critical.

D is critical and has zero slack.   (1 points)

F is critical and has zero slack.

Slack is calculated as?

LFT - EST

LFT - LST

LST - LFT

LFT - EFT   (1 points)

EFT - EST

The amount of time a noncritical task can be delayed without delaying the project is called?

surplus

flop

slack   (1 points)

critical time

safety

Bottom of Form

Project budgets are newly created for each project and often cover several “_____________” in the future.

Projects

Budget Periods   (1 points)

Pay Periods

Scheduling Changes

Reason for cost uncertainty in projects include;

Prices may escalate

Different resources may be required

The project may take a different amount of time than was expected

All of the following   (1 points)

A hybrid gasoline-electric automobiles project is under which project category?

Platform Projects

Derivative Projects

R&D Projects

Resource Projects

Reason for cost uncertainty in projects include;

Prices may escalate

Different resources may be required

The project may take a different amount of time than was expected

All of the following   (1 points)

When looking at the variances on an earned value chart, a positive variance is ___ and a negative variance is ___.

Bad; Good

Good; Good

Good; Bad   (1 points)

Bad; Bad

Top of Form

Which of the following statements regarding critical paths is true?

The shortest of all paths through the network is the critical path.

Some activities on the critical path may have slack.

Every network has only one critical path.

On a specific project, there can be multiple critical paths, all with exactly the same duration.   (1 points)

The duration of the critical path is the average duration of all paths in the project network.

The _________ control takes the form of tests to determine if some specific precondition has been met before permission is granted to continue.

Phase-gate

Go/no-go   (1 points)

Post project

Testing

Bottom of Form

Top of Form

The critical path for the network activities shown below is __________ with duration __________.

| Activity | Duration | Immediate Predecessors |
| --- | --- | --- |
| A | 10 | --- |
| B | 8 | --- |
| C | 2 | A |
| D | 4 | A |
| E | 5 | B,C, D |

A-C; 12

A-D-E; 19   (1 points)

B-E; 13

A-B-C-D-E; 29

none of the above

Which of the following statements regarding CPM is true?

The critical path is the shortest of all paths through the network.

The critical path is that set of activities that has positive slack.

Some networks have no critical path.

All activities on the critical path have their LS equal to the maximum EF of all immediate predecessors.   (1 points)

All of the above are false.

In earned value analysis…

it is desirable to have negative variances for both schedule and spending.

it is desirable to have positive variances for both schedule and spending.   (1 points)

the schedule variance should be positive and the spending variance negative.

the schedule variance should be negative and the spending variance positive.

ideally both variances would equal zero.

Bottom of Form

Which of the following is not a component of a control system?

effector

sensor

decision maker

leveler   (1 points)

standard

Which of the following is not a subprocess of Risk Management?

Risk Development Analysis   (1 points)

Risk Management Planning

Risk Response Planning

Risk Monitoring and Control

What is project slack?

The amount of time a non-critical task can be delayed without making the project late.

The amount of time the critical path of a project can be delayed without making the project late.   (1 points)

The amount of time an activity on the critical path can be delayed without making the project late.

The difference between how long the project would take if all tasks were completed based on their pessimistic versus optimistic time estimates.

None of the above.

EISEL QUESTIONS: 4) Monitoring and Controls

If task duration estimates are carefully made, the project manager needs to only examine the critical path when conducting a risk analysis.

True

False   (0.5 points)

Crashing non-critical activities will influence project duration.

True

False   (0.5 points)

Take the factors considered by earned value analysis and subtract those considered by tracking Gantt charts. The factor(s) you have remaining are:

Cost   (1 points)

Cost and schedule.

Schedule and performance

Performance

Bottom of FormTop of Form

Which of the following is typically used as the best estimate of task duration?

expected time   (1 points)

pessimistic time

optimistic time

most likely time

none of the above

Which of the following terms is most closely associated with a task required by the project?

activity   (1 points)

event

milestone

network

path

Which of the following is not an effective team member's characteristics (excluding the Project Manager)?

Technically competent

High-self esteem

Motivational   (1 points)

Problem orientation

All of the above

For which purpose is simulation NOT used with regard to project scheduling?

to overcome the limitations associated with statistical techniques used to develop probability of completion time estimates

to investigate the range of project completion times

to investigate the distribution of project completion times

to verify the accuracy of the optimistic, pessimistic and most likely time estimates   (1 points)

all of the above

If you have an activity that lasts 4 normal days and 1 crashed day. For the resources, its normal costs is $30 and the crashed cost is 120$. Calculate the cost per day:

-60$/day

90$/day

30$/day

-30$/day   (1 points)

To manage a project successfully, the project manager need only pay close attention to tasks on the critical path.

True

False   (0.5 points)

A project manager that uses milestones as a project control device is using a:

Proactive control system

Predictive control system

Feedback control system

Reactive control system   (1 points)

The actual project duration will be known with certainty after the project is completed.

True   (0.5 points)

False

A project schedule is a project action plan converted into a timetable.

True   (0.5 points)

False

Which of the following is not a subprocess of Risk Management?

Risk Development Analysis   (1 points)

Risk Management Planning

Risk Response Planning

Risk Monitoring and Control

Which of the following is not an input to the schedule control process?

Activity list   (1 points)

Schedule baseline

Performance reports

Schedule management plan

Which of the following is a mechanism by which the PM exerts control?

Process review

Personnel assignment

Resource allocation

All of the above are mechanisms   (1 point

Which of the following is not a component of a control system?

effector

sensor

decision maker

leveler   (1 points)

standard

Which of the following does not affect the duration of a schedule activity?

Resources assigned to the activity

Availability of the assigned resources

Whether the activity is on a critical path   (1 points)

Experience of the human resource assigned

The amount of time a noncritical task can be delayed without delaying the project is called?

surplus

flop

slack   (1 points)

critical time

safety

You are looking into strategies to deal with the negative risks in your project. Which of the following is not a strategy that you can use to deal with negative risks?

Avoid

Transfer

Mitigate

Audit   (1 points)

The purpose of the change control system is to:

Review all requested changes

Identify all impacts the change may have on other project tasks

Ensure that the changes are implemented properly

Communicate accepted changes to all concerned parties

All of the above   (1 points)

The following components are required for project control except;

Sensor

Comparator

Decision maker

Standard

Regulator   (1 points)

Which of the following is NOT a common mistake PMs make when trying to control projects?

Assigning personnel assignments   (1 points)

Excessive control

Across-the-board cuts

Focusing on certain items

The purpose of the change control system is to:

Review all requested changes

Identify all impacts the change may have on other project tasks

Ensure that the changes are implemented properly

Communicate accepted changes to all concerned parties

All of the above   (1 points)

The first step in the control cycle is:

Setting a goal   (1 points)

Measuring progress

Comparing actual with planned performance

Taking action

You are looking into strategies to deal with the negative risks in your project. Which of the following is not a strategy that you can use to deal with negative risks?

Avoid

Transfer

Mitigate

Audit   (1 points)

The first step in the control cycle is:

Setting a goal   (1 points)

Measuring progress

Comparing actual with planned performance

Taking action

The amount of time a noncritical task can be delayed without delaying the project is called?

surplus

flop

slack   (1 points)

critical time

safety

There are many possible rules for assigning preference to some activities over others when allocating scarce resources. What are 4 of the most commonly used priority rules that can be applied to a project?

(4 points)

give preference to critical path 
give preference to least float activity 
give preference to the most complex activity 
give preferences to the activity with most resources first

Take the factors considered by earned value analysis and subtract those considered by tracking Gantt charts. The factor(s) you have remaining are:

Cost   (1 points)

Cost and schedule.

Schedule and performance

Performance

The actual project duration will be known with certainty after the project is completed.

True   (0.5 points)

False

To manage a project successfully, the project manager need only pay close attention to tasks on the critical path.

True

False   (0.5 points)

A project schedule is a project action plan converted into a timetable.

True   (0.5 points)

False

The budgeting approach based on the collective judgments of top and middle managers is called:

top-down budgeting   (1 points)

bottom-up budgeting

activity budgeting

program budgeting

life cycle budgeting

A project manager that uses milestones as a project control device is using a:

Proactive control system

Predictive control system

Feedback control system

Reactive control system   (1 points)

To manage a project successfully, the project manager need only pay close attention to tasks on the critical path.

True

False   (0.5 points)

Task duration is always dictated by the amount of labour required to complete the task.

True

False   (0.5 points

Take the factors considered by earned value analysis and subtract those considered by tracking Gantt charts. The factor(s) you have remaining are:

Cost   (1 points)

Cost and schedule.

Schedule and performance

Performance

What is project slack?

The amount of time a non-critical task can be delayed without making the project late.

The amount of time the critical path of a project can be delayed without making the project late.   (1 points)

The amount of time an activity on the critical path can be delayed without making the project late.

The difference between how long the project would take if all tasks were completed based on their pessimistic versus optimistic time estimates.

None of the above.

A project schedule is a project action plan converted into a timetable.

True   (0.5 points)

False

If task duration estimates are carefully made, the project manager needs to only examine the critical path when conducting a risk analysis.

True

False   (0.5 points)

For which purpose is simulation NOT used with regard to project scheduling?

to overcome the limitations associated with statistical techniques used to develop probability of completion time estimates

to investigate the range of project completion times

to investigate the distribution of project completion times

to verify the accuracy of the optimistic, pessimistic and most likely time estimates   (1 points)

all of the above

Which of the following is not a component of a control system?

effector

sensor

decision maker

leveler   (1 points)

standard

After major risk are identified which of the following data should NOT be obtained for analysis

probability of each risk occurring

Range or distribution of possible outcomes

probability of each outcome

the expected time of each outcome

the person responsible for each outcome   (1 points)

A tracking Gantt chart:

Monitors costs and budget expenditures

Identifies key points in the project's progress

Identifies the stage of completion for each task   (1 points)

Identifies the performance to budget for the overall project by a certain date